## Completions
PP Ref. | Completion Date | Address | Settlement Area | Homes (net) | Use Class | 2022/23 | 2023/24 | Total | Notes
[6 empty] | 236 |  | 236 | Total completions reported in the published 2022/23 AMR.
2016/1066 | 2023-04-01 | 162 Portsmouth Road Thames Ditton Surrey KT7 0XR | Dittons | 16 |  |  | 16 | 16 | Site visit confirmed complete but no completion certificate to prove date.
2017/2534 | 2023-04-01 | St Georges House 24 Queens Road Weybridge Surrey KT13 9UX | Weybridge | 43 |  |  | 43 | 43 | Site visit confirmed complete but no completion certificate to prove date.
2022/0479 | 2023-04-01 | 72B Church Street Weybridge Surrey KT13 8DL | Weybridge | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2021/2890 | 2023-04-01 | 4 Queens Road Hersham KT12 5LS | Hersham | 1 |  |  | 1 | 1 | Same building as 2023/0889 but they relate to different parts of the building.
2023/2150 | 2023-04-01 | 48 Churchfield Road Walton-On-Thames Surrey KT12 2SY | Walton-on-Thames | 1 |  |  | 1 | 1 | Retrospective application. Officer report reflects scheme was already complete at time of application but no dates given.
2018/1504 | 2023-04-01 | 15 Eaton Park Road Cobham KT11 2JJ | Cobham & Oxshott | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2020/1072 | 2023-04-01 | 1 The Mews Albany Crescent Claygate Esher KT10 0PG | Claygate | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2020/2498 | 2023-05-01 | 10 Brittain Road Hersham Walton-On-Thames KT12 4LR | Hersham | 7 |  |  | 7 | 7 | Confirmed by completion certificate.
2020/1972 | 2023-05-12 | Nusrat Lodge 1 Assher Road Hersham Walton-On-Thames KT12 4RA | Hersham | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2021/3090 | 2023-05-01 | 52 - 56 High Street Esher Surrey KT10 9QY | Esher | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2019/2308 2021/2939 | 2023-06-01 | Crow Gables Cottage 133 Fairmile Lane Cobham KT11 2BU | Cobham & Oxshott | 74 | C2 |  | 74 | 74 | Site visit conducted on 07 - 08/05/2024 concluded construction of scheme was completed but no certificate to prove date.
2019/2553 | 2023-06-05 | 4 Fairmile Lane Cobham KT11 2DJ | Cobham & Oxshott | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2020/1540 | 2023-06-26 | 15A Castleview Road, Weybridge, KT13 9AB | Weybridge | 3 |  |  | 3 | 3 | Confirmed by completion certificate.
2020/0308 | 2023-06-01 | Merrileas leatherhead Road Oxshott Leatherhead KT22 0EZ | Cobham & Oxshott | 28 |  |  | 28 | 28 | Confirmed by completion certificate.
2023/0952 | 2023-06-01 | 3 The Island Wey Meadows Weybridge Surrey KT13 8GJ | Weybridge | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2020/3112 | 2023-06-01 | Former 10 Ashley Road Walton-On-Thames KT12 1HU | Walton-on-Thames | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2017/2812 | 2023-08-03 | Land R/o 9 Princes Drive Oxshott Leatherhead Surrey KT22 0UL | Cobham & Oxshott | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2022/2776 | 2023-08-21 | 130-132 Hersham Road Hersham Walton-On-Thames Surrey KT12 5QJ | Hersham | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2017/2433 | 2023-08-04 | 11 Oakfield Glade Weybridge Surrey KT13 9DP | Weybridge | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2019/1160 | 2023-09-15 | Ansell Hall Oakbank Avenue Walton-On-Thames KT12 3RB | Walton-on-Thames | 10 |  |  | 10 | 10 | Confirmed by completion certificate.
2020/2572 | 2023-09-27 | 70 Embercourt Road Thames Ditton KT7 0LW | Dittons | 3 |  |  | 3 | 3 | Confirmed by completion certificate.
2020/1775 | 2023-10-26 | 60 High Street Esher KT10 9TX | Esher | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2018/1627 | 2023-10-25 | 28 Esher Green Esher Surrey KT10 8AF | Esher | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2020/2883 2022/0359 | 2023-10-25 | Hunters Lodge Horsley Road Downside Cobham KT11 3NY | Cobham & Oxshott | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2021/2006 | 2023-11-03 | 6 Thrupps Lane Hersham Walton-On-Thames Surrey KT12 4NF | Hersham | 4 |  |  | 4 | 4 | Confirmed by completion certificate.
2022/3214 | 2023-11-01 | 2 Brunswick Close Walton-On-Thames Surrey KT12 3JJ | Walton-on-Thames | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2018/3812 | 2023-11-03 | Land South of 46 Molesey Park Road West Molesey Surrey KT8 2JZ | Molsey | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2022/3453 | 2023-12-13 | 96 Terrace Road Walton-on-Thames Surrey KT12 2DT | Walton-on-Thames | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2018/2316 | 2023-12-07 | Land Northeast of 70 to 79 Berkeley Court Weybridge KT13 9HY | Weybridge | 3 |  |  | 3 | 3 | Confirmed by completion certificate.
2023/0129 | 2023-12-09 | Flat 4 75 Rydens Avenue Walton-On-Thames Surrey KT12 3JL | Walton on Thames | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2021/1194 | 2023-12-08 | 2A Criterion Buildings Portsmouth Road Thames Ditton KT7 0SS | Dittons | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2018/2819 | 2023-12-20 | Tandem House Queens Drive Oxshott Leatherhead KT22 0PH | Cobham & Oxshott | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2015/3651 | 2023-12-01 | Apps Court Farm, Hurst Road, Walton-On-Thames | Walton on Thames | 14 |  |  | 14 | 14 | Confirmed by completion certificate.
2020/2423 | 2024-01-22 | 42 High Street Walton-On-Thames KT12 1BZ | Walton-on-Thames | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2015/0997 | 2024-01-01 | 46 Portsmouth Road Cobham Surrey KT11 1HY | Cobham & Oxshott | 39 |  |  | 39 | 39 | Confirmed by completion certificate.
2019/3370 | 2024-01-24 | Hillview Nusery Seven Hills Road Walton-On-Thames KT12 4DD | Weybridge | 32 | C2 |  | 32 | 32 | Permission was granted for a 64-bed nursing home. Counted toward completions at a rate of 1.5 as not self contained.
2014/4564 | 2024-01-23 | Land adjacent to 21 Icklingham Road Cobham Surrey KT11 2NQ | Cobham & Oxshott | 2 |  |  | 2 | 2 | Confirmed by completion certificate.
2021/1106 | 2024-01-08 | 40 Baker Street (2nd Floor)Weybridge KT13 8AR | Weybridge | 6 |  |  | 6 | 6 | Confirmed by completion certificate.
2019/1032 | 2024-01-08 | Land Northeast of 49 to 51 High Street Cobham | Cobham & Oxshott | 7 |  |  | 7 | 7 | Confirmed by completion certificate.
2018/2989 | 2024-03-18 | Bridge House 41-45 High Street Weybridge KT13 8BB | Weybridge | 28 |  |  | 28 | 28 | Confirmed by completion certificate.
2021/3991 | 2024-03-01 | Land to South of 94 Manor Road North Esher Surrey KT10 0AE | Hinchley wood and Weston Green | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2021/0944 | 2024-03-18 | 37 Homefield Road Walton-On-Thames KT12 3RE | Walton-on-Thames | 8 |  |  | 8 | 8 | Confirmed by completion certificate.
2020/3299 | 2024-03-18 | Grevillea 125 Silverdale Avenue Walton-On-Thames Surrey KT12 1EH | Walton-on-Thames | 1 |  |  | 1 | 1 | Confirmed by completion certificate.
2020/2299 | 2024-03-01 | 1 & 2 Orchard Cottages Weybridge KT13 9NW | Weybridge | 2 |  |  | 2 | 2 | Site visit conducted on 07 - 08/05/2024 concluded construction of scheme was completed but no certificate to prove date.
2020/1246 | 2024-03-01 | 61A Carlton Road Walton-On-Thames KT12 2DQ | Walton-on-Thames | 2 |  |  | 2 | 2 | Site visit conducted on 07 - 08/05/2024 concluded construction of scheme was completed but no certificate to prove date.
2019/2556 | 2023-10-01 | Site of Stompond Lane Sports Ground Stompond Lane Walton-On-Thames KT12 1HF | Walton-on-Thames | 10 |  |  | 10 | 10 | Development comprises 104 units. 27 units completed in 2021/22, 67 units completed in 2022/23 and 10 units completed in 2023/24 confirmed durin design tour in October 2023. Completion certificate not received for final 10 units.
2019/1287 | 2024-03-01 | Willow House Copse Road Cobham KT11 2TN | Cobham & Oxshott | 1 |  |  | 1 | 1 | Completion confirmed through google street view in May 2024 but no certificate to prove date.
2019/2492 | 2024-03-01 | 10 Woodland Grove Weybridge KT13 9EQ | Weybridge | 1 |  |  | 1 | 1 | Completion confirmed through property sale records on Zoopla. Likely completed in 2021/22 monitoring year as sales in March 2022 but wasn't recorded in that monitoring year and no certificate to prove date.
2019/1703 | 2024-03-01 | Site to Rear of 136 Beauchamp Road KT8 2PH | Molesey | 1 |  |  | 1 | 1 | Completion confirmed through google street view in May 2024 but no certificate to prove date.
2017/0401 | 2024-03-01 | 61-63 More Lane Esher KT10 8AR | Esher | 17 |  |  | 17 | 17 | Completion confirmed through property sale records on Zoopla. Likely completed in 2023/24 monitoring year as sales in March 2024 but no certificate to prove date.
2018/3782 | 2024-03-01 | Claygate House Littleworth Road Esher KT10 9PN | Claygate | 15 |  |  | 15 | 15 | Completion a number of yrs ago confirmed by DM in May 2024 Completion counted in 2023/24 monitoring year as it wasn't recorded in previouis monitoring years and no certificate to prove date.
Total |  |  |  | 406 |  | 236 | 406 | 642

## Under construction
[10 empty] | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
PP Ref. | Type | Decision Date | Commencement Date | Address | Settlement Area | Homes (gross) | Homes (net) | Use Class | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total | Notes | Meets NPPF defintion of Deliverable or Developable
2019/1969 | CoU | 2020-01-10 | 2021-03-08 | 37 The Parade Claygate Esher KT10 0PD | Claygate | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2017/2405 |  | 2018-01-17 | 2021-05-17 | Land South of 54 Foxholes Weybridge Surrey KT13 0BN | Weybridge | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/2211 | Full | 2020-05-12 | 2021-10-05 | Land Northwest of 215 to 217 Portsmouth Road Cobham KT11 1JR | Cobham & Oxshott | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/1805 | Full | 2018-09-10 | 2021-10-13 | Land Southwest of 9 Lower Sand Hills Long Ditton KT6 6RP | Dittons | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/0398 | Full/Sub-Division | 2019-07-04 | 2021-08-06 | 212 Walton Road East Molesey KT8 0HR | Molesey | 2 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2021/0834 | Conv. | 2021-08-23 | 2021-08-10 | Land Rear of 2 Littleheath farm Cottage Steels Lane Oxshott Leatherhead KT22 0RX | Cobham & Oxshott | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2021/0056 | Full | 2021-11-02 | 2022-03-18 | 19 Dale Road Walton-On-Thames KT12 2PY | Walton-on-Thames | 2 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2020/0308 | Full | 2021-02-09 | 2021-03-28 | Merrileas leatherhead Road Oxshott Leatherhead KT22 0EZ | Cobham & Oxshott | 67 | 38 |  | 28 | 38 | [15 empty] | 38 | Cala Homes schemes for 66 units, 22 units completed in 2023/24, with 44 units remaining. Contacted Cala Homes on 16 May 2024 who confirmed site nearing completion. Completion expected end of 2024/start of 2025. | Deliverable
2016/1614 2017/1199 | CoU | 2017-10-03 | 2021-05-26 | Rosemary House Portsmouth Road Esher Surrey KT10 9AA | Esher | 11 | 11 |  |  |  |  | 11 | [13 empty] | 11 | Second and third floor extensions to create 15 additional dwellings. Site between 10 - 20 units. As more time has passed than the average 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/3228 | Full | 2021-05-11 | 2022-03-24 | Land Northeast of 15 Courtlands Avenue Esher KT10 9HZ | Esher | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/2132 | Full | 2018-09-17 | 2018-11-21 | Land to the South of Old Oak March Road Weybridge KT13 8XA | Weybridge | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2020/1020 | CoU | 2020-11-18 | 2021-05-25 | Upper Court Portsmouth Road Esher KT10 9JH | Esher | 56 | 56 | C2 |  | 56 | [15 empty] | 56 | Scheme is 112 bed HMO 56 units at 0.5 rate. Officer site visit in March 2024 reported construction substantially complete and expected to complete by end of 2024/early 2025. Contacted agent at DHA Planning and Development who responded by email on 20 May corroborating site is nearing completion and ready to open very soon with a final few conditional items remaining. | Deliverable
2019/3471 | Full | 2021-03-31 | 2020-05-20 | Bevendean Cottage Warren Lane Oxshott Leatherhead KT22 0SU | Cobham & Oxshott | 15 | 14 |  |  | 14 | [15 empty] | 14 | Contacted agent at Porchester Estates 16 May 2024 who confirmed full completion expected by end of 2024. | Deliverable
2018/0175 | Full | 2019-02-26 | 2019-05-24 | Grantchester House 5 Hinchley Way Esher KT10 0BD | Esher | 1 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/2263 | FUL | 2019-10-11 | 2022-10-04 | Land East Of 13a Station Avenue Walton-On-Thames Surrey KT12 1NF | Walton-on-Thames | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/0187 | PNP | 2019-03-19 | 2022-11-21 | Warehouse 47 Thames Street Weybridge Surrey KT13 8JG | Weybridge | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/1923 | FUL | 2022-02-21 | 2022-11-23 | 18 Heath Ridge Green Cobham KT11 2QJ | Cobham & Oxshott | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2018/0254 | Full | 2019-08-09 | 2022-05-26 | 88 Hurst Road East Molesey KT8 9AH | Molesey | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/1084 | Full | 2023-08-20 | 2022-10-06 | Land adjacent to 58 The Roundway Claygate KT10 0DW | Claygate | 1 | 1 | C3 |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/3441 | PAG/CoU | 2022-12-23 | 2022-11-28 | Beacon House Beacon Mews South Road Weybridge Surrey KT13 9DZ | Weybridge | 1 | 1 | C3 |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/1258 | Full | 2019-08-27 | 2020-12-01 | Nyumbani Ruxley Crescent Claygate Esher KT10 0TZ | Claygate | 2 | 1 |  |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2020/3223 | Full | 2021-06-16 | 2022-05-04 | 8-14 Oatlands Drive Weybridge KT13 9JL | Weybridge | 51 | 47 |  |  | 22 | 25 | [14 empty] | 47 | Applicant submitted s73A application 2024/0726 in March 2023 to retain juliet balcony screens. Site is nearing completion with show homes open and homes up for sale. Contacted agent and applicant but no response received. DM officers advised site nearing completion. Anticipate completion by 2025/26 at latest. | Deliverable
2019/1939 | Full | 2020-04-17 | 2023-03-01 | 41 Onslow Road Hersham Walton-On-Thames KT12 5BA | Hersham | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2018/2260 | Full | 2019-02-27 | 2023-03-01 | Land South of 50 Primrose Road Hersham Walton-On-Thames KT12 5JD | Hersham | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/3830 | FUL | 2023-06-20 | 2023-07-05 | Tintern Court Cavendish Road Weybridge Surrey KT13 0JX | Weybridge | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/1224 | OL | 2022-03-31 | 2023-11-02 | Land South of 8 Arnison Road East Molesey KT8 9JJ | Molesey | 1 | 1 |  |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/0643 | FUL | 2023-05-10 | 2023-10-09 | Land at 90 Fairmile Lane Cobham Surrey KT11 2DA | Cobham & Oxshott | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/3246 | FUL | 2023-02-24 | 2023-10-11 | Beech Shadows 15 Woodside Road Cobham Surrey KT11 2QR | Cobham & Oxshott | 2 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/1797 | FUL | 2022-09-16 | 2023-02-01 | Barn and Land at Silvermere Farm Byfleet Road Cobham Surrey KT11 1DX | Weybridge | 1 | 1 | C3 |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/0812 | FUL | 2022-09-01 | 2023-04-01 | Land adjacent to 15 Hall Place Drive Weybridge Surrey KT13 0AJ | Weybridge | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2018/0632 | Full | 2018-12-05 | 2019-03-04 | Lincoln Court Old Avenue Weybridge Surrey KT13 0PH | Weybridge | 28 | 19 |  |  | 19 | [15 empty] | 19 | Contacted agent at DHA Planning and Development on 17 May 2024 who confirmed site is complete and ready for occupation. | Deliverable
2022/0942 | FUL | 2022-12-02 | 2023-04-01 | 2 Lebanon Drive Cobham Surrey KT11 2PR | Cobham & Oxshott | 2 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/0786 | FUL | 2023-06-01 | 2023-06-01 | Hawthornhill Granville Road Weybridge Surrey KT13 0QG | Weybridge | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/1222 | Full/CoU | 2018-10-18 | 2019-04-08 | 145-149 Hersham Road Hersham Walton-On-Thames KT12 5NR | Hersham | 18 | 16 |  |  |  |  | 16 | [13 empty] | 16 | Second and third floor extensions to create 15 additional dwellings. Site between 10 - 20 units. As more time has passed than the average 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2021/3417 | PNAA | 2021-11-22 | 2022-06-29 | Auckland House New Zealand Avenue Walton-On-Thames Surrey KT12 1PL | Walton-On-Thames | 10 | 10 |  |  | 10 | [15 empty] | 10 | Site between 10 - 20 units. Apply average build out rate of 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. | Deliverable
2023/1241 | PAG | 2023-06-19 | 2023-08-01 | K A D House Portsmouth Road Esher Surrey KT10 9AD | Esher | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/0647 | FUL | 2023-08-14 | 2023-10-01 | 35 Onslow Road Hersham Walton-On-Thames Surrey KT12 5BA | Weybridge | 2 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/0440 | PAM | 2022-04-01 | 2023-12-01 | 33 Creek Road, East Molesey, KT8 9BE | Molesey | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/1139 | FUL | 2023-10-27 | 2024-01-05 | Thames Lodge 129 Thorkhill Road Thames Ditton Surrey KT7 0UN | Thames Ditton | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/3517 | OLA | 2022-08-19 | 2023-03-24 | Oak House 19 Queens Road Weybridge Surrey KT13 9UE | Weybridge | 10 | 10 | C3 |  |  | 10 | [14 empty] | 10 | Site allocation WEY7 allocated for 17 units in draft Local Plan. Site is under construction under outline PP 2021/3517 for net 10 units demolition notice submitted in March 2023. RMs condition 1 of 2021/3517 approved in May 2023. No other RMs to resolve. Discharge of all precommencement conditions confirmed. Including 5 (Material Samples) and 10 (Construction Method Statement) under 2022/3412 confirmed in Feb. 2023; 14 (Tree pre-commencement meeting) under 2023/0173 in Mar. 2023; 19 (Surface water drainage scheme) under 2023/0245 confirmed in May 2023; 21 (Secure by Design) under 2023/0483 confirmed in Jun. 2023. Construction able to start from Jun. 2023. Expect completion 2.5 yrs after commencement (winter 2025) in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2019/3601 | Full | 2021-01-26 | 2023-04-04 | Thamesview House Felix Road Walton-On-Thames KT12 2SL | Walton-On-Thames | 97 | 33 |  |  | 33 | [15 empty] | 33 | PA Housing scheme. Contacted agent at Hill Group 16 May 2024 who confirmed completion expected between Dec. 2024 and Feb. 2025. | Deliverable
2019/3430 | Full | 2020-10-14 | 2020-12-02 | 28 Esher Road Hersham Walton-On-Thames KT12 4LG | Hersham | 3 | 2 |  |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2017/0419 |  | 2017-12-15 | 2021-02-22 | Site of 18 19 And 21 St Johns Drive Walton-On-Thames Surrey KT12 3NH | Walton-on-Thames | 3 | 2 |  |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/0244 | Full | 2018-05-22 | 2021-05-26 | 28-30 High Street Weybridge Surrey KT13 8AB | Weybridge | 3 | 2 |  |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/1933 | Full | 2018-10-22 | 2021-07-06 | Oxford House Leatherhead Road Oxshott Leatherhead Surrey KT22 0ET | Cobham & Oxshott | 3 | 2 |  |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/2005 | CoU/Full | 2021-09-28 | 2022-05-31 | Units 1 & 2 Hampton Court Estate Summer Road Thames Ditton KT7 0RG | Dittons | 78 | 78 |  |  |  | 78 | [14 empty] | 78 | Birchgrove homes site. Construction up to roof level confirmed. Applicant submitted S73 application 2024/0172 to amend design in Jan. 2024. Contacted agent and developer on 22 May 2024 who confirmed all 78 units expected to be delivered in 2025/26. Additional information for outstanding conditions recently submitted to EBC and hoping to have EA comments by start of August and then discharge conditions. Also confirmed S73 application immaterial to delivery timeframe and units. | Deliverable | 2020
2019/0386 | Full | 2020-06-22 | 2022-01-10 | St Catherines Thames Street Weybridge KT13 8JR | Weybridge | 28 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2018/0492 | Full | 2018-07-17 | 2019-04-17 | 28 Red Lane Claygate Esher KT10 0ES | Esher | 2 | 2 |  |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/2378 | Full | 2020-03-06 | 2023-03-02 | 5 Central Avenue West Molesey KT8 2QX | Molesey | 2 | 2 |  |  | 2 | [15 empty] | 2 | Amended by 2022/3367 but units remain the same. Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/4104 | Full | 2022-03-11 | 2022-05-26 | Foxholes Stokesheath Road Oxshott Leatherhead KT22 0PP | Cobham & Oxshott | 3 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/3413 | Full | 2022-02-04 | 2022-06-16 | 9 Water Lane Cobham KT11 2PA | Cobham & Oxshott | 3 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2018/3678 | Full | 2019-10-18 | 2022-06-16 | 1-5 Hillside Portsmouth Road Esher KT10 9LJ | Esher | 18 | 13 | [6 empty] | 13 | [11 empty] | 13 | Contacted agent at Pegasus Planning on 17 May 2024 who confirmed subsequent application 2023/3173 submitted in Nov. 2023 for 38 units is what they intend to implement. If PP is not secured applicant will take it to appeal and will ultimately sell site if they fail at appeal. Agent advised that it is likely that first units on extant permission would not be delivered until 2028/2029 at earliest with an anticipated 2 year build. Assuming July 2024 consent for 2023/3173, Applicant/Developer Beechcroft developments will exercise option and anticipate build out of scheme with first units delivered 2025/26 and completion in 2027/28. | Deliverable
2019/2119 | Full | 2020-04-08 | 2022-06-20 | Warling Dean 33 New Road Esher KT10 9PG | Esher | 19 | 12 |  |  | 12 | [15 empty] | 12 | Site between 10 - 20 units. Apply average build out rate of 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. | Deliverable
2018/3671 | Full | 2019-07-23 | 2022-07-15 | Site of 45 to 55 Waverley Road 1 and 3 Lyfield and 4 to 10 Webster Close Oxshott | Cobham & Oxshott | 23 | 11 |  |  | 11 | [15 empty] | 11 | Site between 10 - 20 units. Apply average build out rate of 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. | Deliverable
2019/1588 | Full | 2019-04-02 | 2023-01-09 | Land Adjacent to 39 Charlton Avenue Hersham Walton-On-Thames KT12 5LE | Hersham | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/2814 | FUL | 2022-11-28 | 2023-02-01 | The Waffrons Woodstock Lane South Chessington Surrey KT9 1UF | Dittons | 3 | 2 | C3/E |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/2095 | Full | 2020-06-18 | 2022-10-31 | Site of Claygate House Littleworth Road Esher KT10 9PN | Claygate | 62 | 62 |  |  | 62 | [15 empty] | 62 | Part of wider site Claygate House. PA 2019/1047 for conversion of office floorspace to C3 completed in 2021/22 delivering 59 units. 2019/1047 related to Claygate House, the Rythe Building and Link Building along with associated car parking facilities, open space etc. 2020/2095 relates to Pavilion building, a single storey storage/garage building, areas for car parking and vehicular circulation, a swimming pool and amenity space/soft landscaping. Red line boundaries on site plans for each PP clearly show the seperation. Shanly homes site. Construction well advanced. Sales office on site and properties up for sale. Contacted agent 16 May 2024 who confirmed site nearing completion and ready for occupation in Oct/Nov. 2024. No completions recorded in 2023/24. | Deliverable
2021/0160 | FUL | 2021-12-20 | 2023-06-14 | 16 Stevens Lane Claygate Esher KT10 0TE | Claygate | 3 | 2 |  |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/1212 | FUL | 2022-12-05 | 2023-09-04 | Land Southeast of 39 Stoke Road Stoke D'Abernon Cobham Surrey KT11 3BH | Cobham & Oxshott | 2 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/0086 | PNA | 2022-03-17 | 2022-12-02 | Beechcroft Manor Weybridge KT13 9NY | Weybridge | 11 | 11 |  |  |  | 11 | [14 empty] | 11 | Site between 10 - 20 units. Apply average build out rate of 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. | Deliverable
2021/0395 | PNA | 2021-05-26 | 2022-12-12 | Two Oaks Castleview Road Weybridge KT13 9AA | Weybridge | 12 | 12 |  |  |  | 12 | [14 empty] | 12 | Site between 10 - 20 units. Apply average build out rate of 2.5 yrs from commencement to completion for sites of 10 - 49 units in the Borough. | Deliverable
2023/0177 | FUL | 2023-08-03 | 2023-12-04 | 41 Riverside Road Hersham Walton-On-Thames Surrey KT12 4PH | Walton-on-Thames | 3 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/0149 | FUL | 2023-03-24 | 2023-11-21 | Blue Barn Farm Blue Barn Lane Weybridge Surrey KT13 0NH | Weybridge | 2 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/2569 | Full | 2021-04-21 | 2022-09-28 | 412 Walton Road West Molesey KT8 2JG | Molesey | 50 | 38 |  |  | 26 | 12 | [14 empty] | 38 | Rushmon Homes site. Construction started on site in June 2023 with construction on 26 AH units in Block A starting in Oct. 2023. Contacted Rushmon Homes who confirmed completion of Block A of 26 AH units which have been handed over to PA Housing. Commencement of Block B with 24 units expected in Nov. 2024 | Deliverable
2018/0160 | Conv | 2018-10-08 | 2018-10-11 | 16 Monument Green Weybridge KT13 8QT | Weybridge | 4 | 3 |  |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/2670 | Full | 2020-01-13 | 2020-04-15 | Land to Rear of 41 Oatlands Chase Weybridge KT13 9RP | Weybridge | 3 | 3 |  |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2020/2614 | Full | 2021-09-17 | 2021-11-16 | 106 Walton Road East Molesey KT8 0HP | Molesey | 4 | 3 |  |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2021/3596 | PNMA | 2021-12-08 | 2022-01-31 | 6 AC Court High Street Thames Ditton KT7 0SR | Dittons | 13 | 5 |  |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2020/3048 | Full | 2021-06-28 | 2021-11-15 | 1 Portsmouth Avenue Thames Ditton KT7 0RW | Dittons | 4 | 3 |  |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/3494 | OL | 2019-05-03 | 2022-04-21 | Horsley Bungalow Old Avenue Weybridge KT13 0PS | Weybridge | 4 | 3 |  |  | 3 | [15 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/2127 | Full | 2022-02-28 | 2022-05-31 | Linbridge Oatlands Avenue Weybridge KT13 9TR | Weybridge | 4 | 3 |  |  | 3 | [15 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/3946 | FUL | 2022-04-29 | 2022-01-06 | Land West of 1 to 3 High Street and Trenchard Arlidge Oakshade Road Oxshott Leatherhead Surrey KT22 0JU | Cobham & Oxshott | 3 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Unreliable commencement date recorded. Expect completions within 3 yrs of base date due to uncertainty around start date. | Deliverable
2022/3676 | FUL | 2023-06-27 | 2023-09-05 | Tall Trees Four Acres Cobham Surrey KT11 2EB | Cobham & Oxshott | 4 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/2469 | Full | 2020-06-22 | 2023-11-24 | 32 Green Lane Cobham KT11 2NN | Cobham & Oxshott | 4 | 3 |  |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/2376 | FUL | 2023-05-17 | 2023-11-21 | 4 Fernhill Oxshott Leatherhead Surrey KT22 0JH | Cobham & Oxshott | 4 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Site allocation COS7 allocated for 5 units in draft Local Plan. S73 application for variation of condition 2 (approved plans) of PP 2022/2376 submitted in Feb. 2024. Decision target date 01 May 2024. Deed of variation of PP 2022/2376 to amend the Section 106 Early and Late Review Mechanism for AH submitted in April 2024. Target decision date 18 Jun. 2024. Expect completion 2 yrs after commencement (Nov 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2020/0145 | CoU | 2020-06-12 | 2023-02-01 | Admiral Rodney House 17 Church Street Walton-On-Thames Surrey KT12 2QT | Walton-on-Thames | 3 | 3 |  |  | 3 | [15 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/0862 | PNM | 2021-05-06 | 2023-04-01 | 5 High Street Esher KT10 9RL | Esher | 3 | 3 |  |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/2309 | Full | 2020-12-30 | 2022-05-27 | 9 Leigh Court Close Cobham KT11 2HT | Cobham & Oxshott | 5 | 4 |  |  | 4 | [15 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2019/1813 | FUL | 2021-10-18 | 2023-07-26 | The Royal Cambridge Home, 82-84 Hurst Road East Molesey KT8 9AH (C2) | Molesey | 32 | 2 | C2 |  | 2 | [15 empty] | 2 | PP 2019/1813 granted for 60 bed extra care (C3) and 32 bed car home (C2). 32 bed care home not self contained therefore counted at a rate of 1:0.5 giving 16 units. 28 existing care home rooms at 1:0.5 gives 14 units. Therefore net of 2 units associated with care home component of scheme. Contacted agent at Verve Planning on 17 May 2024 who confirmed phase 1 (the C2 care home complenet) due for completion end of July 2024. | Deliverable
2021/4359 | FUL | 2022-05-04 | 2024-01-31 | Land to rear of 38 and 41 Twinoaks Cobham Surrey KT11 2QP | Cobham & Oxshott | 4 | 4 | C3 |  |  | 4 | [14 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2022/2631, 2023/2396 | FUL | 2023-07-10 | 2024-02-29 | Land West of 9 Cricket Way Weybridge Surrey KT13 9LP | Weybridge | 5 | 4 | C3 |  |  | 4 | [14 empty] | 4 | Site allocation WEY11 allocated for 20 units in draft Local Plan. Expect completion 2 yrs after commencement (Feb. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2019/0792 | Full | 2019-11-06 | 2020-05-01 | 1 Green Lane Cobham KT11 2NN | Cobham & Oxshott | 6 | 5 |  |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2017/3397 | Full | 2018-10-17 | 2019-06-05 | 55 Weston Avenue West Molesey KT8 1RG | Molesey | 6 | 5 |  |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/2520 | OL | 2018-12-04 | 2021-09-26 | Elmer Dene 95 Queens Road Hersham Walton-On-Thames Surrey KT12 5LA | Hersham | 6 | 5 |  |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2018/3193 | Full | 2019-02-05 | 2018-10-25 | 70 Baker Street Weybridge Surrey KT13 8AL | Weybridge | 5 | 5 |  |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2022/1998 2021/2764 | FUL | 2022-11-24 | 2022-10-18 | 16 Sandy Lane Walton-on-Thames Surrey KT12 2EQ | Walton-on-Thames | 6 | 5 | C3 |  | 5 | [15 empty] | 5 | Site allocation WOT8 allocated for 7 units in draft Local Plan. Discharge of condition 3 (Material Samples), 6 (Electric Vehicle Charging), 7 (Construction Transport Management Plan) and 8 (Potential Land Contamination) of 2021/2764 under 2022/2040 confirmed in Sep. 2022; conditon 6 (Electric vehicle charging) 7 (Construction management plan) 8 (Potential land contamination) and 9 (Landscaping scheme) of 2022/1998 under 2022/3745 confirmed in part / refused in part in Mar. 2023. S73 application for variation of Condition 2 (Approved plans) of 2022/1998 granted in Mar. 2023. NMA to PP 2022/3688 granted in May 2024. Deed of variation to remove the Early and Late Review Mechanism for Viability from PP 2022/2388 submitted April 2024. Decision target date Jun. 2024. Expect completion 2 yrs after commencement (Oct. 2024) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2019/0575 | FUL | 2020-07-16 | 2023-07-07 | Land East of 82 Island Farm Road West Molesey KT8 2LQ | Molesey | 5 | 5 | C3 |  |  | 5 | [14 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/2626 | FUL/CoU | 2022-12-02 | 2023-10-03 | Administration Block Octagon Road Whiteley Village Hersham Walton-On-Thames Surrey KT12 4EG | Weybridge | 5 | 5 | C3 |  |  | 5 | [14 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2023/2311 | COU | 2023-11-24 | 2024-01-08 | 63 Bridge Road East Molesey Surrey KT8 9ER | Molesey | 8 | 5 | C3 |  |  | 5 | [14 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/2254 | FUL | 2022-05-31 | 2022-06-16 | Copsem Manor 50 Copsem Lane Esher Surrey KT10 9HJ | Cobham & Oxshott | 6 | 6 | C3 |  | 6 | [15 empty] | 6 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/4194 | Full | 2022-10-31 | 2022-12-08 | 142 High Street Esher Surrey KT10 9QJ | Esher | 6 | 6 | C3 |  | 6 | [15 empty] | 6 | 6 units reflects amendment 2023/0491. Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/1431 | Full | 2021-12-07 | 2023-04-01 | 5 Hinchley Way Esher Surrey KT10 0BD | Esher | 6 | 6 | C3 |  |  | 6 | [14 empty] | 6 | Site allocation D4 allocated for 6 units in draft Local Plan. Expect completion 2 yrs after commencement (April 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2023/1791 | PAM | 2023-08-18 | 2023-10-01 | AC Court Unit 7 7 High Street Thames Ditton KT7 0SR | Thames Ditton | 6 | 6 | C3 |  |  | 6 | [14 empty] | 6 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/1243 | Sub-Division | 2020-11-13 | 2021-06-10 | The Lodge 29A Palace Road East Molesey KT8 9DJ | Molesey | 8 | 7 |  |  |  |  | 7 | [13 empty] | 7 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2019/3163 | Full | 2020-07-20 | 2022-02-08 | Garage Block Ikona Court Weybridge | Weybridge | 7 | 7 |  |  |  |  | 7 | [13 empty] | 7 | Small site between 1 - 9 units. As more time has passed than the average 2 yrs from commencement to completion for sites of 1 - 9 units in the Borough. Expect completions within 3 yrs of base date to build in contingency in case of further delays. | Deliverable
2021/3269 | FUL | 2022-09-16 | 2022-11-01 | Cold Norton Farm Ockham Lane Cobham Surrey KT11 1LW | Cobham & Oxshott | 7 | 7 | C3 |  | 7 | [15 empty] | 7 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2021/4404 | FULL | 2022-05-25 | 2023-02-01 | 39 Charlton Avenue Hersham Walton-On-Thames Surrey KT12 5LE | Hersham | 7 | 7 | C3 |  | 7 | [15 empty] | 7 | Small site between 1 - 9 units. Apply average build out rate of 2 yrs to completion from commencement date. | Deliverable
2020/1795 | FUL | 2021-10-05 | 2024-10-05 | Merrywood Weston Green Thames Ditton KT7 0JZ | Thames Ditton | 26 | 25 | C3 |  | 25 | [15 empty] | 25 | Developer Sigma Homes Group contacted 17 May 2024 who confirmed construction nearing completion. First homes occupied in April 2024. Next phase of occupations in June/July 2024 with full completion and handover/completion of housing association block also expected by end of July 2024. | Deliverable
2021/1399 | Outline | 2022-05-01 | 2025-05-01 | Heath Lodge St Georges Avenue Weybridge Surrey KT13 0DA | Weybridge | 13 | 13 | C3 |  | 13 | [15 empty] | 13 | Site allocation WEY9 allocated for 2 units in draft Local Plan. Applicant - Surrey Rest Homes Limited. Contacted agent at Union Arch 15 May 2024 who confirmed scheme is implemented and nearing completion with just internal fit out to complete. Completion anticipated by Sep. 2024. | Deliverable
2021/0183 | Full | 2022-01-05 | 2024-03-01 | Land at Downside Road Cobham KT11 3LY | Cobham & Oxshott | 27 | 26 | C3 |  | 15 | 11 | [14 empty] | 26 | Site under construction confirmed March 2024. Applicant has submitted several subsequent s73 applications. NMA 2024/0543 submitted in Feb. 2024 allow the site to be developed in two phases. Phasing Layout Plan indicates Phase 1 to deliver 15 units (8 of which are AH) with Phase 2 to deliver 12 units (3 of which are AH). Construction on Phase 1 of 15 units confirmed March 2024. Contacted applicant and agent but no response recieved. Apply phasing of two blocks indicated by applicant and anticipate completion 2.5 yrs from commencement (Autumn/Winterr 2026). | Deliverable
Total | [5 empty] | 1010 | 763 |  | 28 | 423 | 225 | 102 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763
Note on AB24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check if any completions on record for this one.

## PP (small sites <10)
[10 empty] | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
PP Ref. | Type | Decision Date | Expiry Date | Address | Settlement Area | Homes (gross) | Homes (net) | Use Class | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total | Notes | Meets NPPF defintion of Deliverable or Developable
2021/0766 | LDCP | 2021-04-07 | 2024-04-07 | 27B High Street Weybridge KT13 9AX | Weybridge | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1218 | CoU | 2021-05-21 | 2024-05-21 | 11 St Marys Long Ditton KT6 5EU | Dittons | 6 | 5 | C2 |  | 5 | [15 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1708 | Full | 2021-05-24 | 2024-05-24 | 20 The Drive Cobham KT11 2JQ | Cobham & Oxshott | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/0749 | Full | 2021-06-29 | 2024-06-29 | 31 Hurstfield Road West Molesey KT8 1QU | Molesey | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/0290 | Full | 2021-08-03 | 2024-08-03 | 4 Churchfield Road Walton-On-Thames KT12 2TF | Walton-on-Thames | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/2078 | PNAA | 2021-08-11 | 2024-08-11 | 9 Esher Road Hersham Walton-On-Thames KT12 4JZ | Hersham | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1306 | Full | 2021-08-12 | 2024-08-05 | 37 Rectory Lane Long Ditton Surbiton KT6 5HP | Dittons | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2019/2416 | Full | 2021-08-23 | 2024-08-23 | Willow Cottage Ridgeway Close Oxshott Leatherhead KT22 0LQ | Cobham & Oxshott | 5 | 4 |  |  | 4 | [15 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/1552 | LDCP | 2021-08-25 | 2024-08-25 | 85 Queens Road Weybridge KT13 9UQ | Weybridge | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1149 | OL | 2021-09-07 | 2024-09-07 | 8 Holtwood Road Oxshott KT22 0QJ | Cobham & Oxshott | 5 | 4 |  |  | 4 | [15 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/0826 | Full | 2021-09-10 | 2024-09-10 | 360 Walton Road West Molesey KT8 2JE | Molesey | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/2043 | PNO | 2021-10-05 | 2024-10-29 | Unit C St Georges Business Park Brooklands Road Weybridge KT13 0TS | Weybridge | 6 | 6 |  |  | 6 | [15 empty] | 6 | Unlikely to be implemented, will lapse in Oct. 2024. Applicant has not made progress with discharge of conditions and lodged appeal in Jan. 2024 against refusal of 2023/2170 for 10 houses and 43 apartments on site is included within - St Georges Business Park. The Council has argued in the Inquiry that applicant does not have enough time to implement the PA and does not intend to, having submitted 4 new applications for PA, including 2024/1305, 2024/1306, 2024/1307 and 2024/1309, which would superseed the existing PAs. However, non-implementation discount of 10% applied to small sites will reflect this. Contacted agent at Newsteer in May 2024 but no response received. | Deliverable
2020/2562 | Full | 2021-10-14 | 2024-10-14 | Garage Block West of 11 Arran Way Esher KT10 8BE | Esher | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2563 | Full | 2021-10-14 | 2024-10-14 | Garage Block North of 47 and West of 49 Douglas Road Esher KT10 8BA | Esher | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2096 | Full | 2021-10-25 | 2024-10-25 | White Lodge Hogshill Lane Cobham KT11 2AL | Cobham & Oxshott | 2 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2608 | Full | 2022-02-15 | 2025-02-15 | Garage Block South of 33 to 45 The Roundway Claygate Esher KT10 0DP | Claygate | 2 | 2 |  |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/0202 | Full | 2022-03-02 | 2025-03-02 | Waterside Hampton Court Way East Molesey | Molesey | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/0201 | Full | 2022-03-23 | 2025-03-23 | 16 Lakeside Drive Esher KT10 9EZ | Esher | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1629 | Full | 2022-03-25 | 2025-03-25 | Garage Block South of 2 and 4 Wyndham Avenue Cobham KT11 1AT | Cobham & Oxshott | 3 | 3 |  |  | 3 | [15 empty] | 3 | Site allocation COS3 allocated for 4 units in the draft Local Plan. No subsequent applications submitted. Expect completion 3 yrs after decision date (March 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2020/3499 | FUL | 2021-11-11 | 2024-11-11 | Garages and playground to the side and rear of 61- 69 Rodney Road 24-30 Ambleside Avenue 10-12 Edgehill Court and Flats 7- 11 12-14 St Johns Drive Surrey | Walton-on-Thames | 6 | 6 | C3 |  | 6 | [15 empty] | 6 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/0653 | FUL | 2022-06-27 | 2025-06-27 | 20 New Road Esher Surrey KT10 9PG | Esher | 4 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/1239 | PAF | 2022-07-20 | 2025-07-20 | 1-15 Hillbrook Gardens Weybridge KT13 0SP | Weybridge | 5 | 5 | C3 |  |  | 5 | [14 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1932 | FUL | 2022-05-16 | 2025-05-16 | 187A Cottimore Lane Walton-On-Thames Surrey KT12 2BX | Walton-on-Thames | 4 | 4 | C3 |  |  | 4 | [14 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/4341 | FUL | 2022-06-07 | 2025-06-07 | 32-34 High Street Walton-On-Thames Surrey KT12 1BZ | Walton-on-Thames | 2 | 2 | C3/ HMO |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/3072 | OLA | 2022-06-08 | 2025-06-08 | 363 to 367 Molesey Road Walton-On-Thames Surrey KT12 3PF | Walton-on-Thames | 7 | 6 | C3 |  |  | 6 | [14 empty] | 6 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2500 | FUL | 2022-07-15 | 2025-07-15 | Garages along Foxwarren to the rear of 115-125 Covert Road Claygate Esher Surrey | Claygate | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2107 | FUL | 2022-07-20 | 2025-07-20 | 111 Hersham Road Walton-On-Thames Surrey KT12 1RN | Walton-on-Thames | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/2962 | FUL | 2021-11-09 | 2024-11-09 | Land Southwest of Arenella Mountview Road Claygate Esher Surrey KT10 0UD | Claygate | 1 | 1 |  |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/3663 | FUL | 2022-08-05 | 2025-08-05 | 102-106 High Street Esher Surrey KT10 9QJ | Esher | 2 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1628 | FUL | 2022-08-23 | 2025-08-23 | 13 Garages to the rear of 27 and 27a Wyndham Avenue Cobham | Cobham & Oxshott | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/0698 | FUL | 2022-09-09 | 2025-09-09 | Land South of, 3 Southwood Manor Farm Burhill Road Hersham Surrey KT12 4BJ | Hersham | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1613 | FUL | 2022-09-30 | 2025-09-30 | Garages to the rear of 132-152 Tartar Road Cobham Surrey | Cobham & Oxshott | 5 | 5 | C3 |  |  | 5 | [14 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2815 | PAM | 2022-11-04 | 2025-11-04 | 244 Walton Road, West Molesey, KT8 2HT | Molesey | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2491 | PDT | 2022-11-25 | 2025-11-25 | 23-27 High Street Cobham Surrey KT11 3DH | Cobham & Oxshott | 3 | 3 | C3/E |  |  | 3 | [14 empty] | 3 | Not a duplicate of 2022/1231. PA for additional storey on existing building. Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/3231 | PAG/CoU | 2022-12-16 | 2025-12-16 | 55 - 57 Bridge Road East Molesey Surrey KT8 9ER | Molesey | 2 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/4263 | FUL | 2022-12-23 | 2025-12-23 | 6 Snellings Road Hersham Walton-On-Thames Surrey KT12 5JG | Hersham | 2 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2129 | FUL | 2023-01-27 | 2026-01-27 | 58A High Street Walton-on-Thames Surrey KT12 1BY | Walton-on-Thames | 3 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/3795 | PAM | 2023-02-23 | 2026-02-09 | 254 Walton Road West Molesey Surrey KT8 2HT | Molesey | 1 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2339 | FUL | 2023-02-13 | 2026-02-13 | 32 Hersham Road Walton-On-Thames Surrey KT12 1UX | Walton-on-Thames | 3 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/0441 | FUL | 2023-03-08 | 2026-03-08 | Land North West of Campbell Cottage & 1 Beacon Mews South Road Weybridge Surrey KT13 9DZ | Weybridge | 2 | 2 | C3 |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/3003 | FUL | 2023-03-24 | 2026-03-24 | Garage block North of 54 and West of 52 Belvedere Gardens West Molesey Surrey KT8 2TD | Molesey | 4 | 4 | C3 |  |  | 4 | [14 empty] | 4 | Site allocation MOL5 allocated for 4 units in draft Local Plan. No subsequent application submitted. Expect completion 3 yrs after decision date (Mar. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2022/1342 | FUL | 2023-03-09 | 2026-03-09 | 4A Palace Road East Molesey Surrey KT8 9DL | Molesey | 2 | 1 | C3 |  |  | 1 | [14 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1627 | Full | 2021-05-04 | 2024-05-04 | Lock Up Garages Waverley Road Oxshott | Cobham & Oxshott | 4 | 4 | C3 |  | 4 | [15 empty] | 4 | Site allocation COS5 allocated for 6 units in the draft Local Plan. No subsequent applications submitted. Expect completion 3 yrs after decision date (Nov. 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2020/0582 | FUL | 2021-10-27 | 2024-10-27 | Claremont House, 34 Molesey Road, Hersham, KT12-4RQ | Hersham | 6 | 6 | C3 |  | 6 | [15 empty] | 6 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/3350 | Full | 2021-10-18 | 2024-10-18 | 4 and 4A Castleview Road Weybridge KT13 9AB | Weybridge | 2 | 2 | C3 |  | 2 | [15 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/0114 | Full | 2021-07-16 | 2024-07-16 | Fairmile Farm Cottage Denby Road Cobham KT11 1JY | Cobham & Oxshott | 1 | 1 | C3 |  | 1 | [15 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/3769 | Outline | 2022-05-01 | 2025-05-01 | Southlands 40 Queens Road Weybridge Surrey KT13 0AR | Weybridge | 3 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/1928 | Full | 2022-05-01 | 2025-05-20 | 143 Molesey Avenue,West Molesey, KT8 2RY | Molesey | 3 | 3 | C3 |  |  | 3 | [14 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/3286 | FUL | 2023-05-05 | 2026-05-04 | 1 and 2 High Street Oxshott Leatherhead Surrey KT22 0JN | Cobham & Oxshott | 2 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/2566 | FUL | 2023-05-23 | 2026-05-23 | Garages North of 37 to 43 Blair Avenue Esher Surrey | Esher | 2 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Site allocation D11 allocated for 4 units in the draft Local Plan. No subsequent application submitted. Expect completion 3 yrs after decision date (May 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2022/2816 | FUL | 2023-05-31 | 2026-05-31 | Land to the East of 40 Oatlands Chase Weybridge Surrey KT13 9RT | Weybridge | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2020/1626 | FUL | 2023-06-01 | 2026-06-01 | Garage Block between 46 -48 Middleton Road Downside Cobham Surrey KT11 3NR | Cobham & Oxshott | 3 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Site allocation COS10 allocated for 3 units in draft Local Plan. No subsequent applications submitted. Expected to complete 3 yrs after decision date (June 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2021/3348 | FUL | 2023-06-01 | 2026-06-05 | Cedar House Mill Road Cobham Surrey KT11 3AL | Cobham & Oxshott | 3 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Site allocation COS1 allocated for 7 units. No subsequent applications submitted. Expected to commence 1 yrs after decision date (Jun. 2024), with completion 3 yrs after decision date (Jun. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2022/3724 | FUL | 2023-06-01 | 2026-06-01 | Land Southwest of Grace Land Molember Road East Molesey Surrey KT8 9NH | Molesey | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1124 | PAM | 2023-06-08 | 2026-06-08 | 516 Walton Road West Molesey Surrey KT8 2QF | Molesey | 4 | 4 | C3 |  |  |  | 4 | [13 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0807 | PAM | 2023-06-30 | 2026-06-30 | Bridge House 72 Bridge Road East Molesey Surrey KT8 9HF | Molesey | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/1672 | FUL | 2023-07-07 | 2026-07-07 | Holly Lodge 68 Stoke Road Stoke D'Abernon Cobham Surrey KT11 3PX | Cobham & Oxshott | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1242 | PAM | 2023-07-12 | 2026-07-12 | 25-27 High Street Esher Surrey KT10 9RL | Esher | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/1400 | FUL | 2023-07-19 | 2026-07-19 | Garage Block Bennett Close Cobham Surrey KT11 1AJ | Cobham & Oxshott | 3 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Site allocation COS11 allocated for 4 units in the draft Local Plan. No subsequent applications submitted. Expect completion 3 yrs after decision date (July 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2022/1260 | COU | 2023-07-20 | 2026-07-20 | 27 High Street Thames Ditton Surrey KT7 0SD | Thames Ditton | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/1690 | FUL | 2023-07-25 | 2026-07-25 | 52 Manor Road South Esher Surrey KT10 0QQ | Esher | 3 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2378 | FUL | 2023-09-14 | 2026-09-14 | 5 Bridge Road East Molesey Surrey KT8 9EU | Molesey | 2 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1871 | COU | 2023-09-19 | 2026-09-19 | Flat 96 Terrace Road Walton-On-Thames Surrey KT12 2DT | Walton-on-Thames | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/1215 | FUL | 2023-10-02 | 2026-10-02 | 71 A High Street Walton-on-Thames Surrey KT12 1DN | Walton-on-Thames | 3 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0889 | COU | 2023-10-10 | 2026-10-10 | 4 Queens Road Hersham Walton-On-Thames Surrey KT12 5LS | Walton-on-Thames | 2 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1184 | FUL | 2023-10-12 | 2026-10-12 | 49 and 50 High Street Oxshott Leatherhead Surrey KT22 0JP | Cobham & Oxshott | 5 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2091 | FUL | 2023-10-12 | 2026-10-12 | 103 Ashley Road Walton-On-Thames Surrey KT12 1HL | Walton-on-Thames | 6 | 5 | C3 |  |  |  | 5 | [13 empty] | 5 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2327 | PAM | 2023-10-18 | 2026-10-18 | 133A Hersham Road Walton-On-Thames Surrey KT12 1RW | Walton-on-Thames | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2021/2350 | PAM | 2023-10-23 | 2026-10-23 | 44 Octagon Road Whiteley Village Hersham Walton-On-Thames Surrey KT12 4EA | Walton-on-Thames | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2417 | PAM | 2023-10-23 | 2026-10-23 | 30 Monument Green Weybridge Surrey KT13 8QW | Weybridge | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1792 | FUL | 2023-11-01 | 2026-11-01 | Land West Of, 18 Riverside Road Hersham Walton-On-Thames Surrey KT12 4PE | Walton-on-Thames | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2361 | PAM | 2023-11-10 | 2026-11-10 | 6 Baker Street Weybridge Surrey KT13 8AU | Weybridge | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2526 | FUL | 2023-11-24 | 2026-11-24 | 13 Sidney Road Walton-On-Thames Surrey KT12 2NA | Walton-on-Thames | 2 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0787 | FUL | 2023-12-08 | 2026-12-08 | 1A Locke King Road Weybridge Surrey KT13 0SY | Weybridge | 3 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1043 | FUL | 2023-12-19 | 2026-12-19 | 6 Pine Grove Weybridge Surrey KT13 9AX | Weybridge | 5 | 4 | C3 |  |  |  | 4 | [13 empty] | 4 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1884 | FUL | 2023-12-01 | 2026-12-01 | 28 Green Lane Hersham Walton-On-Thames Surrey KT12 5HD | Walton-on-Thames | 2 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0145 | Full | 2023-06-01 | 2026-06-30 | Conifers Old Avenue Weybridge Surrey KT13 0QD | Weybridge | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/1123 | PAM | 2023-06-01 | 2026-06-01 | 92 Thorkhill Road Thames Ditton Surrey KT7 0UQ | Thames Ditton | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2847 | Full | 2023-08-01 | 2026-08-04 | 37 and 39 Queens Road Hersham Walton-on-Thames Surrey KT12 5NE | Walton-on-Thames | 3 | 2 | C3 |  |  |  | 2 | [13 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0304 | Outline | 2023-05-01 | 2026-05-26 | Land rear of 90 Esher Road East Molesey KT8 0AG | Molesey | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0453 | Full | 2023-04-01 | 2026-04-25 | 20 Effingham Road, Long Ditton, Surbiton, KT6 5JY | Dittons | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2022/2811 | Full | 2023-05-01 | 2026-05-01 | Ambleside, 3, The Spinney, Queens Drive, Oxshott, Leatherhead, KT22 0PL | Cobham & Oxshott | 2 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Site allocation COS20 allocated for 8 units in draft Local Plan. No subsequent applications submitted. Expect completion 3 yrs after decision date (May 2027) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable
2022/0439 | PNMA | 2022-04-07 | 2025-04-07 | 29-31 Creek Road East Molesey Surrey KT8 9BE | Molesey | 2 | 2 |  |  |  | 2 | [14 empty] | 2 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2998 | PA | 2024-01-12 | 2027-01-12 | Holmesdale Bridgewater Road Weybridge Surrey KT13 0EG | Weybridge | 3 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/3416 | PA | 2024-02-05 | 2027-02-05 | 8A High Street Esher Surrey KT10 9RT | Esher | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2366 | Full | 2024-03-14 | 2027-03-14 | 19 Old Esher Road Hersham Walton-On-Thames Surrey KT12 4LA | Walton-on-Thames | 4 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2698 | Full | 2024-03-14 | 2027-03-14 | 40 Fleetside West Molesey Surrey KT8 2NF | Molesey | 1 | 1 | C3 |  |  |  | 1 | [13 empty] | 1 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/0291 | Full | 2024-01-01 | 2027-01-01 | 270 Brooklands Road, Weybridge, Surrey, KT13 0QX | Weybridge | 9 | 8 |  |  |  |  | 8 | [13 empty] | 8 | Small site between 1 - 9 units. Apply average build out rate of 1 yr to commencement and 3 yrs to completion from decision date. | Deliverable
2023/2776 | Full | 2024-01-01 | 2027-01-01 | 35 New Road, Esher, KT10 9DW | Esher | 4 | 3 | C3 |  |  |  | 3 | [13 empty] | 3 | Site allocation ESH5 and allocated for 5 units in draft Local Plan. Applicant progressing with discharge of conditions under 2024/1081 submitted in Apr. 2024. Expect completion 3 yrs after decision date (Jan. 2027) in line with average build out rates for sites of 1 - 9 units in the Borough. Site considered deliverable but will come forward as windfall development. | Deliverable
Total | [5 empty] | 225 | 196 |  | 0 | 62 | 59 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196

## PP (medium & large sites 10+)
[10 empty] | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
PP Ref. | Type | Decision Date | Expiry Date | Address | Settlement Area | Homes (gross) | Homes (net) | Use Class | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total | Notes | Meets NPPF defintion of Deliverable or Developable
2020/2176 | Full | 2021-08-23 | 2024-08-23 | Greenways 46 Copsem Lane Esher KT10 9HJ | Cobham & Oxshott | 22 | 21 | [18 empty] | 0 | Applicant has not made progress with discharge of conditons. Contacted agent at Urban Matrix in May 2024 but no response received. Subsequent outline application submitted for care home use (C2) and 2 semi-detached homes (C3) 2022/3822 was refused in March 2023. Expiration of 2020/2176 in Aug. 2024. Suggests unlikely to implement.
2021/2579 | PNA | 2021-09-10 | 2024-09-10 | Beechwood Court Station Avenue Walton-On-Thames KT12 1LT | Walton-on-Thames | 10 | 10 |  |  | 10 | [15 empty] | 10 | Site between 10 - 20 units. Apply average build out rate of 3 yrs to completion from decision date in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2021/2591 | PNO | 2021-09-10 | 2024-09-10 | Walton Lodge Bridge Street Walton-On-Thames KT12 1BT | Walton-on-Thames | 20 | 20 | [5 empty] | 20 | [12 empty] | 20 | Contacted agent Montague Evans in May 2024 but no response recieved. Applicant submitted subsequent pre-app 2022/1160 for 51 units in 2022. Pre-app indicates intention to develop site but likely at higher density than extant PP which is due to expire in Sep. 2024. No progress made with discharge of conditions however, a subsequent application for PA was submitted to the Council w/c 20 May 2024 that seeks to renew the current PA that will expire in Sept. 2021. Site may still be deliverable if the replacement PA is approved in 2024 could anticipate completion 3 yrs later under the replacement PA by the end of 2027 in line with the average build out rates for sites of 10 - 20 units in the Borough. | Deliverable
2021/2625 | PNO | 2021-09-29 | 2024-09-29 | Idis House Churchfield Road Weybridge KT13 8DB | Weybridge | 24 | 24 | [18 empty] | 0 | Applicant has not made progress with discharge of conditons. Expiration in Sep. 2024. Contacted agent in May 2024 but no response received. No subsequent applications received. Suggests unlikely to implement.
2021/1950 | PNO | 2021-10-07 | 2024-10-07 | Building C 207 Brooklands Road Elder House Weybridge KT13 0RH | Weybridge | 20 | 20 | [5 empty] | 20 | [12 empty] | 20 | Unlikely to be implemented, will lapse in Oct. 2024. Applicant has not made progress with discharge of conditions and lodged appeal in Jan. 2024 against refusal of 2023/2170 for 10 houses and 43 apartments on site is included within - St Georges Business Park. Site may still be deliverable as applicant has submitted 4 new applications for PA, including 2024/1305, 2024/1306, 2024/1307 and 2024/1309, which would replace the existing PAs that are about to expire. However, as of the 2024/25 base date PA will expire. If the replacement PA is approved in 2024 could anticipate completion 3 yrs later under the replacement PA by the end of 2027 in line with the average build out rates for sites of 10 - 20 units in the Borough. Contacted agent at Newsteer in May 2024 but no response received. | Deliverable
2021/2807 | PNO | 2021-10-15 | 2024-10-15 | 241 Brooklands Road Weybridge KT13 0RH- Building D | Weybridge | 32 | 32 | [5 empty] | 32 | [12 empty] | 32 | Unlikely to be implemented, will lapse in Oct. 2024. Applicant has not made progress with discharge of conditions and lodged appeal in Jan. 2024 against refusal of 2023/2170 for 10 houses and 43 apartments on site is included within - St Georges Business Park. Site may still be deliverable as applicant has submitted 4 new applications for PA, including 2024/1305, 2024/1306, 2024/1307 and 2024/1309, which would replace the existing PAs that are about to expire. However, as of the 2024/25 base date PA will expire. If the replacement PA is approved in 2024 could anticipate completion 3 yrs later under the replacement PA by the end of 2027 in line with the average build out rates for sites of 10 - 20 units in the Borough. Contacted agent at Newsteer in May 2024 but no response received. | Deliverable
2021/2808 | PNO | 2021-10-15 | 2024-10-15 | 243 Brooklands Road Weybridge KT13 0RH- Building E | Weybridge | 17 | 17 | [5 empty] | 17 | [12 empty] | 17 | Unlikely to be implemented, will lapse in Oct. 2024. Applicant has not made progress with discharge of conditions and lodged appeal in Jan. 2024 against refusal of 2023/2170 for 10 houses and 43 apartments on site is included within - St Georges Business Park. Site may still be deliverable as applicant has submitted 4 new applications for PA, including 2024/1305, 2024/1306, 2024/1307 and 2024/1309, which would replace the existing PAs that are about to expire. However, as of the 2024/25 base date PA will expire. If the replacement PA is approved in 2024 could anticipate completion 3 yrs later under the replacement PA by the end of 2027 in line with the average build out rates for sites of 10 - 20 units in the Borough. Contacted agent at Newsteer in May 2024 but no response received. | Deliverable
2019/1813 | Full | 2021-10-18 | 2024-10-18 | The Royal Cambridge Home, 82-84 Hurst Road East Molesey KT8 9AH (C3) | Molesey | 60 | 60 |  |  |  | 20 | 20 | 20 | [12 empty] | 60 | 2019/1813 - PP granted for 60 bed extra care (C3) and 32 bed car home (C2). 32 bed care home component of scheme is under construction. 60 bed extra care facility will provide self contained units therefore counted at rate of 1:1. Condition 21 Parking discharged under 2024/0468 in April 2024. Contacted agent at Verve Planning on 17 May 2024 who confirmed phase 1 (the C2 care home component) due for completion end of July 2024. Phase 2 (C3 extra care component) contractors are moving into site and setting up facilities by end Aug 2024, anticipate commencement by Sep. 2024, with completion in summer 2026. Discharge of pre-commencement conditions due to be submitted in coming weeks. Apply average build out rate of 20 dpa for sites of 50 - 99 units from Lichfields Start to Finish (Third Edition). | Deliverable
2021/0092 | Full | 2022-01-05 | 2025-01-05 | 7 Ashley Road Walton-on-Thames KT12 1HY | Walton-on-Thames | 18 | 17 |  |  | 17 | [15 empty] | 17 | Site between 10 - 20 units. Apply average build out rate of 3 yrs to completion from decision date in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2021/2698 | PNO | 2022-04-14 | 2025-04-14 | 6 The Heights Weybridge Surrey KT13 0XP | Weybridge | 21 | 21 | [5 empty] | 21 | [12 empty] | 21 | Discharge of conditions confirmed in Nov. 2022 under 2022/2576 but no work started on site. Applicant came in for pre-app for C2 use in 2023. Contacted agent at Quod in May 2024 but no response received. PP can be implemented up to April 2025. Apply average build out rate of 2.5 yrs from commencement to completion (end of 2027) for sites of 10 - 49 units in the Borough. | Deliverable
2022/1231 | PAM | 2022-07-01 | 2025-07-01 | 23-27 High Street Cobham Surrey KT11 3DH | Cobham & Oxshott | 10 | 10 | C3 |  |  | 10 | [14 empty] | 10 | PA Housing scheme for change of use of existing commerical building. Site between 10 - 20 units. Apply average build out rate of 3 yrs to completion from decision date in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2021/1791 | FUL | 2022-05-31 | 2025-05-31 | 45 More Lane Esher Surrey KT10 8AP | Esher | 25 | 25 | C3 |  | 25 | [15 empty] | 25 | Site allocation ESH11 allocated for 25 units in draft Local Plan. S73 application for variation of condition 2 approved plans of 2021/1791 granted PP under 2022/2392 in Feb. 2023. Second S73 for variation of condition 2 approved plans of 2022/2392 granted PP under 2022/2392 in Dec. 2023. Discharge of all pre-commencement conditions of PP 2021/1791 under 2022/2691 confirmed in Nov 2023. Officers confirmed work on site is underway with commencement notice expected in the 3 - 6 months. Contacted developer Octagon Housing on 17 May 2024 who confirmed anticipate completion in Aug./Sep. 2024. | Deliverable
2018/3810 | FUL | 2022-07-19 | 2025-07-19 | Jolly Boatman and Hampton Court Station Redevelopment Area Hampton Court Way East Molesey KT8 9AE | Molesey | 97 | 97 | [18 empty] | 0 | Railways Act issue currently being considered by Secretary of State in relation to whether building is over 50 ft high. Also ongoing DCMS issue. No conditions discharged to date. PP due to expire in Jul. 2025. Contacted agent at Rapleys 17 May 2024 who confirmed issues with Railways Act and DCMS ongoing with decisions anticipated in the summer of 2024 at the earliest. As such, applicant is unable to estimate a start and completion timeframe and PP is due to expire in Jul. 2025. Agent confirmed high risk PP won't be implemented.
2023/0714 | PAM | 2023-05-02 | 2026-05-02 | Building B 205 St Georges Business Park Brooklands Road Weybridge Surrey KT13 0BG | Weybridge | 16 | 16 | C3 |  |  |  |  | 16 | [12 empty] | 16 | Applicant has not made progress with discharge of conditions and lodged appeal in Jan. 2024 against refusal of 2023/2170 for 10 houses and 43 apartments on site is included within - St Georges Business Park. Site may still be deliverable as applicant has submitted 4 new applications for PA, including 2024/1305, 2024/1306, 2024/1307 and 2024/1309, which would replace the existing PAs that are about to expire. However, as of the 2024/25 base date PA will expire. If the replacement PA is approved in 2024 could anticipate completion 3 yrs later under the replacement PA by the end of 2027 in line with the average build out rates for sites of 10 - 20 units in the Borough. Contacted agent at Newsteer in May 2024 but no response received. | Deliverable
2021/1192 | Full | 2021-10-21 | 2024-10-21 | Britannia House Pool Road West Molesey Surrey KT8 2AB | Molesey | 87 | 87 | C3 | [17 empty] | 0 | To be built in 4 blocks - phasing per block. 87 units reflects latest s73 application which reduced units from 97 to 87. Contractors ARJ fell through which has led to delay in commencing on site. ARJ have gone into administration and ceased trading in April 2024. DM officers confirmed in May 2024 no commencement to date and given situation with developer the PP is likely to expire.
2022/2746 | Full | 2023-07-01 | 2026-07-01 | Members Hill, Brooklands Road | Weybridge | 176 | 176 | C2 |  |  |  |  | 49 | 49 | 49 | 29 | [9 empty] | 176 | Scheme is C2 but all self contained units so counted to supply at rate of 1:1. 176 units reflects latest s73 application which reduced units from 205 to 176. Agent at Savills contacted 17 May 2024 who confirmed commencement anticipated in 2024 through demolition work but could not confirm date of first completions. Apply average of 3 yrs from commencement to first completions (2027) with build out rate of 49 dpa in line with Lichfields Start Finish (Third Edition) research for sites of 100 - 499 units. | Deliverable
2023/3355 | PA | 2024-01-17 | 2027-01-17 | Unit 1 A C Court High Street Thames Ditton Surrey KT7 0SR | Thames Ditton | 12 | 12 | C3 |  |  |  | 12 | [13 empty] | 12 | Site between 10 - 20 units. Apply average build out rate of 3 yrs to completion from decision date in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2023/0798 | Full | 2024-03-22 | 2027-03-22 | Crown House Church Road Claygate Esher Surrey KT10 0BF | Esher | 14 | 14 | C3 |  |  |  | 14 | [13 empty] | 14 | Site allocation CL6 allocated for 12 units in the draft Local Plan. No subsequent applications submitted. Expected to commence 1.3 yrs after decision date (summer 2025), with completion 3 yrs after decision date (March 2027) in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable
2021/0744 | Full | 2021-08-23 | 2024-08-23 | Childs Play Centre Manor Road Walton-On-Thames KT12 2PH | Walton-on-Thames | 19 | 19 | C3 | [17 empty] | 0 | PA Housing scheme. Subseqeunt PP 2022/1145 granted for temporary use of the site as a nursery. No progress made with discharge of conditions. Contacted PA Housing in May 2024 who confirmed they are anticipating bringing forward a new application to replace 2021/0744. Therefore unlikely to implement. | Developable
2022/1680 | Full | 2024-02-09 | 2027-02-09 | 9-21a High Street Walton-On-Thames Surrey KT12 1DG | Walton-on-Thames | 61 | 61 | C3 |  |  |  |  | 20 | 21 | 20 | [10 empty] | 61 | Site allocation WOT4 allocated for 71 units and commercial floorspace in draft Local Plan. No subsequent application submitted. Discharge of precommencement conditions required. Including 3 (Materials samples), 5 (Asbestos Containing Materials), 6 (Noise Insulation), 11 (SuDS), 13 (Sensitive Lighting Management Plan), 14 (Ecological Enhancement Plan), 18 (Construction Transport Management Plan), 20 (Potential Contaminated Land). No progress to date. Contacted agent at Barton Willmore on 17 May 2024 who confirmed work is progressing with applications for discharge of conditions. They anticipate commencement of AH component of scheme in 2 yrs (May 2026) and first completions in 3 - 4 yrs (May 2027 - 2028). Expected further detail on build out rate from developer but not recieved. Apply average build out rate of 20 dpa for sites of 50 - 99 units from Lichfields Start to Finish (Third Edition). | Deliverable
Total | [5 empty] | 761 | 759 |  | 0 | 52 | 30 | 46 | 215 | 70 | 69 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511

## Resolution to Grant
[9 empty] | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
PP Ref. | PP Type | Decision Date | Address | Settlement Area | Homes (gross) | Homes (net) | Use Class | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total | Notes | Meets NPPF defintion of Deliverable or Developable
2023/1359 | Resolution to Grant | 2023-12-05 | Brooklands College, Heath Road, Weybridge, KT13 8TT | Weybridge | 320 | 320 | C3 |  |  | 27 | 160 | 48 | 71 | 14 | [10 empty] | 320 | Resolution to Grant subject to s106 agreement given in Dec. 2023. PP granted April 2024. Developer Cala Homes provided anticipated build out rate per calendar yr based on a mid May 2024 start in email correspondence dated 15 Mar. 2024. In further conversations with developer on 24 May 2024. They confirmed commencement due 01 July 2024 with work on progressing discharge of conditions ongoing. | Deliverable
2022/1272 | Resolution to Grant | 2024-03-12 | Abbey House Wellington Way Weybridge KT13 0TT | Weybridge | 106 | 106 | C3 |  |  |  |  | 49 | 49 | 8 | [10 empty] | 106 | Construction of a single building of 3 to 7 storeys. Resolution to grant in Mar. 2024. s106 agreement with SCC to agree and sign before PP granted and decision issued. Anticipate s106 signed and decision notice issued by end of 2024 at latest. Pre-commencement conditions include highways improvements (improved ped crossings, bus stop improvements) which need to be agreed and secured with s278 with SCC. Anticipate 1 - 2 years to secure s278, discharge pre-commencement conditons and commencement on site (end of 2026) in line with Lichfields Start to Fnish (Second Edition) for sites of 100 - 499 units. Contacted applicant Sorban Estates and agent Richard Henley but no response recieved. Anticipate first completions 3 yrs after decision (late 2028/early 2029) and a built out rate of 49 dpa again in line with Lichfields Start to Finish (Third Edition) for schemes of 100 - 499 units. | Deliverable
Total | [5 empty] | 426 |  | 0 | 0 | 27 | 160 | 97 | 120 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426

## Sites allocations
[5 empty] | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
Site ref. | Site Address | Settlement Area | Total Allocation (net) | Use Class | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total | Notes | Meets NPPF defintion of Deliverable or Developable | 5 Year Period | Key
CL1 | Torrington Lodge Car Park, Hare Lane, Claygate | Claygate | 8 | [6 empty] | 8 | [10 empty] | 8 | EBC owned site allocated for net 8 units in draft Local Plan. EBC AMPS confirmed site is to be brought forward for delivery in the 6 - 10 yr period of the Plan in May 2024. A mixed use scheme including an M&S and 8 units has been developed with viability and feasibility studies undertaken. Council currently producing a place making vision for Claygate is expected to be adopted in the next yr. Anticipate PP recieved in the next yr or two and 1 yr for the application to be determined. Then apply the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2029/30. | Developable | 6 to 10 years |  | Site should be removed from site allocations.
CL2 | Garages to the rear of Foxwarren, Claygate | Claygate | 0 | [17 empty] | 0 | PA Housing site identified in 2018 Urban Capacity Study [HOU012] and allocated for 5 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence |  |  | Site is under construction or has Planning Permission.
CL3 | Garages to the rear of Holroyd Road, Claygate | Claygate | 0 | [17 empty] | 0 | PA Housing owned site allocated for 3 units in draft Local Plan. Application for full PP 2021/0349 submitted in Feb. 2021. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Deliverable but will fall into windfall category. | 1 to 5 years |  | C2 use
CL4 | Hare Lane Car Park, Hare Lane, Claygate | Claygate | 0 | [17 empty] | 0 | EBC owned site allocated in draft Local Plan for 7 units. EBC AMPS confirmed that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
CL5 | Claygate Centre, Elm Road, Claygate, KT10 0EH | Claygate | 14 | [15 empty] | 14 |  | 14 | EBC owned site allocated for the repovision of the existing community use and 14 units in draft Local Plan. No plans developed and EBC AMPS confirmed in May 2024 that site has been leased for dementia care services for 5 years. EBC AMPS confirmed there are no short term plans to develop a residential scheme to implement when the lease ends. However, they consider it to be a developable site and a scheme could be worked up in the next 10 year that could be delivered in the 11 - 16 yr period of the Plan. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give time for a scheme to be developed and implemented after the 5 year lease is up. Also reflecting the need to reprovide the existing community use which could impact lead in time. | Developable | 11 - 15 years
CL6 | Crown House, Church Road, Claygate, KT10 0BF | Claygate | 0 | [17 empty] | 0 | Allocated for 12 units in the draft Local Plan. Granted PP under 2023/0798 in March 2024 for net 14 units. No subsequent applications submitted. Expected to commence 1.3 yrs after decision date (summer 2025), with completion 3 yrs after decision date (March 2027) in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable | 1 to 5 years
CL7 | Claygate Station Car Park, The Parade | Claygate | 0 | [17 empty] | 0 | Identified 2018 Urban Capacity Study [HOU012] and allocated for 15 units in the draft Local Plan. The site is owned by Network Rail who have not confirmed it is avaliable for development. Previous grant of permission for residential development in 2005. Whilst Network Rail have not confirmed availability, the site is considered developable based on the evidence of the urban capacity study. A scheme could be worked up in the next 10 yrs that could be delivered in the 11 - 16 yr period. In light of the uncertainty, delivery pushed back to the end of the Plan period (2038/39 - 2039/40) to give time for a scheme to be developed and implemented. | Not enough evidence
COS1 | Cedar House, Mill Road, Cobham, KT11 3AL | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 7 units. Application for full PP and LBC granted under 2021/3348 for net 3 units in Jun. 2023. No subsequent applications submitted. Expected to commence 1 yrs after decision date (Jun. 2024), with completion 3 yrs after decision date (Jun. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
COS2 | Cedar Road Car Park, Cedar Road, Cobham, KT11 2AA | Cobham, Oxshott and Stoke D'Abernon | 5 | [15 empty] | 5 |  | 5 | EBC owned site allocated for 5 units in draft Local Plan. No plans developed and EBC AMPS confirmed in May 2024 that no plans have been developed to date and there are no short term plans to do so. However, they consider it to be a developable site and a scheme could be worked up in the next 10 years that could be delivered in the 11 - 16 yr period of the Plan. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give around 10 yrs for a scheme to be developed and 4 yrs to be implemented. | Developable | 11 to 15 years
COS3 | Site B Garages at Wyndham Avenue, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 4 units in the draft Local Plan. PP granted under 2020/1629 in March 2022 for net 3 units. No subsequent applications submitted. Expect completion 3 yrs after decision date (March 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS4 | Garages to the rear of 6-24 Lockhart Road, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 3 units in the draft Local Plan. PP granted under 2020/1612 in May 2024 for net 3 units. No subsequent applications submitted. Expected to complete 3 yrs after decision date (May 2027) in line with average build out rates for sites of 1 - 9 units in the Borough. As such, site will likely come forward as windfall development. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS5 | Garages at Waverley Road, Oxshott | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 6 units in the draft Local Plan. PP 2020/1627 granted on appeal in Nov. 2022 for net 4 units. No subsequent applications submitted. Expect completion 3 yrs after decision date (Nov. 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS6 | 40 Fairmile Lane, Cobham, KT11 2DQ | Cobham, Oxshott and Stoke D'Abernon | 13 | [10 empty] | 13 | [6 empty] | 13 | Allocated for 13 units in draft Local Plan. Application for full PP 2022/3547 for net 17 units refused in Aug. 2023. Reasons for refusal include: 1. Due to its inappropriate scale, massing, appearance and layout, the proposal would result in overdevelopment of the site which would be out keeping with the character of the area and detrimental to the street scene. 2. The proposal, due to the positioning of windows, change in levels and proximity to neighbouring properties would result in undue overlooking / loss of privacy. 3. The proposal, due to its location, size and extent of works within the root protection areas of protected trees and an unacceptable juxtaposition between structures and important trees. 4. The proposal would fail to provide an appropriate level of parking 5. Due to the inadequate size of the proposed bin store, its siting and lack of information regarding its practicalities, the development would fail to provide appropriate waste and recycling facilities. 6. The proposal, by reason of the lack of a completed legal agreement, fails to secure the necessary contribution towards SAMM for the Thames Basin Heath SPA. 7. The proposal, by reason of the lack of a completed legal agreement, fails to secure the necessary contribution towards affordable housing. Refusal hasn't been taken to appeal and no subsequent applications submitted. Refused scheme was of greater density than allocated in draft Plan. Council considers the reasons for refusal could be overcome with a scheme more aligned to the density proposed in the allocation. Based on the above, the site is considered to be developable with delivery in the 6 - 10 yr period of the Plan. As it a small major development (10 - 20 units) and could be built out relatively quickly, applicants could submit an application in the next 5 years for a lower density scheme and the site could be delivered by the end of the 6 - 10 yr period, provide around 1 yr for determination and 3 yrs to completion from decision in the line with the average build out rates for schemes of 10 - 49 units in the Borough would anticipate completion in 2033/34. | Developable | 6 to 10 years
COS7 | 4 Fernhill, Oxshott, KT22 0JH | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 5 units in draft Local Plan. Site is under construction under 2022/2376 for net 3 units, with commencement on site in Nov 2023. Discharge of all pre-commencement conditions confirmed under 2023/3408 in Feb. 2024. S73 application for variation of condition 2 (approved plans) of PP 2022/2376 submitted in Feb. 2024. Decision target date 01 May 2024. Deed of variation of PP 2022/2376 to amend the Section 106 Early and Late Review Mechanism for AH submitted in April 2024. Target decision date 18 Jun. 2024. Expect completion 2 yrs after commencement (Nov 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS8 | 52 Fairmile Lane, Cobham, KT11 2DF | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 7 units in draft Local Plan. Landowner entered pre-app discussions with Council on scheme of 9 gross units - 8 net in 2021. Council concluded principle of development was acceptable in pre-app response. Site is considered developable based on the evidence in the pre-app however, no application has been submitted to date. Contacted agent 23 May 2024 who confirmed developer has not yet bought the land and likely not intending to come forward with an application in the short term. However, site is considered developable based on the pre-app evidence. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS9 | Pineview, Fairmile Park Road, Cobham, Kt11 2PG | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 6 units in draft Local Plan. Council received confirmation from landowner that the site is available for development and could come forward in the 6 - 10 yr period of the Plan in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Landowner entered pre-app discussion on a scheme of 6 units with the Council in 2021. Council concluded principle of development was acceptable. Contacted agent on 23 May 2024 who confirmed landowner still keen to develop the site but does not have short term plans to submit an application. However, site is considered developable based on the pre-app evidence. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS10 | Garage block, Middleton Road, Downside | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 3 units in draft Local Plan. Granted PP for net 3 units under 2020/1626 in June 2023. No subsequent applications submitted. Expected to complete 3 yrs after decision date (June 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
COS11 | Garages at Bennett Close, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 4 units in the draft Local Plan. Granted PP under 2022/1400 for net 3 units in July 2023. No subsequent applications submitted. Expect completion 3 yrs after decision date (July 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
COS12 | Glenelm and 160 Anyard Roads, Conham, KT11 2LH | Cobham, Oxshott and Stoke D'Abernon | 26 |  |  |  | 26 | [13 empty] | 26 | Allocated for 34 units in draft Local Plan. Outline application 2023/2889 for net 26 units under consideration submitted 20 Oct. 2023. Made valid 05 Dec. 2023 with comments due by 21 May 2024. Decision target date 14 Jun. 2024. Expect to take to committee and issue decision in July 2024. RM on landscaping will be required and typical pre-commencement conditons. Proposal includes off site highway works including a new pedestrian crossing on Portsmouth Road, likely to be Grampian condition. Applicant is Shanly Homes Ltd. Applicant's planning statement dated Oct. 2023 states that the site is able to deliver within the current 5 year period (2023/24 - 2028/29) at paragraph 5.5. Contacted agent on 22 May 2024 who confirmed if PP is granted in July 2024 anticipate commencement in Q1 2025 and completion in Q3 2026. | Deliverable | 1 to 5 years
COS13 | 1 Goldrings Road, Oxshott, Leatherhead, KT22 0QP | Cobham, Oxshott and Stoke D'Abernon | 9 | [10 empty] | 9 | [6 empty] | 9 | Identified and allocated for 32 units in the draft Local Plan in light of pre-app discussions with Council for a scheme of 65 bed care home and 40 extra care apartments in 2019. This was not supported by the Council, as there was not a need for market extra care homes in the Borough. Subsequent pre-app received in 2023 for 1 Goldrings for 9 units under 2023/1374. 1 of the 3 landowners of the site confirmed availability for development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is considered developable based on the pre-app evidence and response from the landowner. However, no application has been submitted to the Council and 2 landowners have not provided notification of availability. In light of the uncertainty around the availability of the site. Push delivery back to the end of the Plan period (2038/39 - 2039/40). Giving around 10 yrs for a scheme to be worked up and submitted and 4 yrs to be determined and built out in line with the average build out rates in the Borough. | Developable | 6 to 10 years
COS14 | Cobham Centre for the Community, Lushington Drive, Cobham, KT11 2LU | Cobham, Oxshott and Stoke D'Abernon | 37 | [15 empty] | 15 | 22 | 37 | EBC owned site allocated for 37 units in draft Local Plan. EBC AMPS confirmed that the reference to the village hall on the site in the Regulation 19 Plan was an error. The site was intended to only be the community centre. This does not have an impact on the quantum allocated as the village hall was not included in the capacity assessment. No plans have been developed to date but in May 2024 EBC AMPS confirmed site is developable and could be brought forward for delivery in the 11 - 16 yr period of the Plan. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give time around 10 yrs for a scheme to be developed and 4 yrs to be implemented. | Developable | 6 to 10 years
COS15 | 87 Portsmouth Road, Cobham, KT11 1JH | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in the 2018 Urban Capacity Study [HOU012] and allocated for 10 units in draft Local Plan. Landowner confirmed site available for devleopment in the 6 - 10 yr period of the Plan in response to land ownership and availability checks carried out in 2018. No response received from landowner in 2023. Site is currently in retail use and no application or pre-app has been submitted to the Council. Given site is currently in retail use with an opertional retail unit and landowner appears to no longer consider it available for development. The site is no longer considered to be available. | No longer available
COS16 | Cobham Health Centre and Garages off Tartar Road | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified through Identified in 2018 Urban Capacity Study [HOU012] but was not considered to be viable due to the community facilties on site. The Council conisdered the site to be developable through a mixed use scheme incorporating and reproviding the community facilities and allocated for it 11 units in the draft Local Plan. Site is considered developable based on discussions between the landowners and the Council over email in 2019 but no pre-app or application has been submitted. As the site is allocated for small major development (10 - 20 units) it is considered that an application could come forward and be built out relatively quickly with little lead in time. However, as there are mutliple landowners on the site lead it time could be impacted. Therefore, delivery anticipated in the 11 - 16 yr period (from 2037/38) giving around 10 yrs for a scheme to be worked up and submitted and 4 yrs to be determined and built out in line with the average build out rates for sites of 10 - 49 units in the Borough. | Not enough evidence
COS17 | Selden Cottage and Ronmar, Leatherhead Road, KT22 0EX | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 18 units in draft Local Plan. Council review of housing trajectory in support of appeal inquiry of refused application 2023/0962 for Land North of Raleigh Drive, Claygate concluded 18 units is not achieavable and the site will likely come forward as a windfall development. Full PP 2023/2316 granted for 4 units in April 2024. Expected to complete 3 yrs after decision date (April 2027) in line with average build out rate of sites of 1 - 9 units in the Borough. | Allocated quantum unachievable. Will fall into windfall.
COS18 | 73 Between Streets, Cobham, KT11 1AA | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | SCC owned site allocated for 40 units in draft Local Plan. SCC granted PP 2023/3209 for children's home (C2) with rooms for 4 residents and 2 staff in Dec. 2023 on part of site. Units are not self contained are are therefore counted towards housing supply at a 1:0.5 rate giving 3 units. Site could therefore fall into windfall category. Expected to commence 1 yr after decision date (Dec. 2025) and complete 3 yrs after decision date (Dec. 2027) in line with Borough average build out rates for schemes of 1 - 9 units. Council received confirmation from SCC that in addition to the children's home they intend to bring forward a scheme for 3 - 4 units on the site in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. No plans have been developed yet and SCC confirmed scheme will be brought forward in the 11 - 15 year period of the draft Plan. A scheme of 3 - 4 units will likely come forward as a windfall devleopment. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS19 | St Andrew's Church, Oakshade Road, Oxshott, KT22 0LE | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for community use.
COS20 | Ambleside, 3 The Spinney, Queens Drive, KT22 0PL | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated for 8 units in draft Local Plan. Granted PP under 2022/2811 in May 2024 for net 1 unit. No subsequent applications submitted. Expect completion 3 yrs after decision date (May 2027) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
COS21 | Coveham House, Downside Bridge Road and The Royal British Legion, Hollyhedge Road, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 14 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Developable
COS22 | Shell Fairmile, 270 Portsmouth Road, Cobham KT11 1HU | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 10 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
COS23 | 68 Between Streets and 7-11 White Lion Gate, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 6 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS24 | Above Waitrose, 16-18 Between Streets, Cobham KT11 1AF | Cobham, Oxshott and Stoke D'Abernon | 20 | [9 empty] | 20 | [7 empty] | 20 | Although the 2018 Urban Capacity Study [HOU012] identified the site but it was not considered deliverable. However, Council consider the site to be developable through a scheme delivered above the existing building and it was allocated for 20 units in the draft Local Plan. The Council received a response confirming an interest in development in the long term to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study but no pre-app or application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Developable | 6 to 10 years
COS25 | Garages and parking to the rear of Cobham Gate, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS26 | Tiltwood Care Home, Hogshill Lane, Cobham, KT11 2AQ | Cobham, Oxshott and Stoke D'Abernon | 24 | [15 empty] | 24 |  | 24 | SCC owned site allocated for 88 C2 beds (24 units at 0.5 rate) in draft Local Plan. Tiltwood is a listed building held on lease until 2027. No plans have been developed yet and SCC haven't made a decision on use of site beyond 2027 but have confirmed that if the decision is made to release after lease ends in 2027 the site will be released for housing development. Site is therefore considered developable in the 11 - 16 yr period of the Plan. As the site is a relatively small major development (21 - 49 units) the lead in times can be relatively short. However, given the uncertainty around the site, with SCC to formally decide on its use beyond 2027, delivery pushed back to 11 - 16 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 6 - 10 yr period or later in the early part of the 11 - 16 yr period, giving up to 10 yrs for a scheme to be worked up, could anticipate completions in the later part of the 11 - 16 yr period from 2038/39. | Developable | 11 to 15 years
COS27 | Ford Garage, 97 Portsmouth Road, Cobham, KT11 1JJ | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 21 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
COS28 | Premier Service Station, 101 Portsmouth Road, Cobham, KT11 1JN | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 7 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS29 | Protech House, Copse Road, Cobham KT11 2TW | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Sutdy [HOU012] and allocated for 28 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Asssessment. The site is considered developable based on the evidence in the urban capacity study. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (21 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forwared in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units in the Borough to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Not enough evidence
COS30 | 38 Copse Road, Cobham, KT11 2TW | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but not considered deliverably due to overlooking issues. However, the Council considered these issues could be overcome with a well designed scheme and allocated it for 7 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
COS31 | 20 Stoke Road, Cobham | Cobham, Oxshott and Stoke D'Abernon | 8 | [8 empty] | 8 | [8 empty] | 8 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in draft Local Plan. Council received confirmation from landowner that site is available in the 6 - 10 yr period of the Plan and has capacity to achieve 8 units in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site considered developable based on the evidence in the Urban Capacity Study and response recieved from the landowner but no application or pre-app has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
COS32 | Sainsbury's car park, Bridge Way, Cobham, KT11 1HW | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 58 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
COS33 | BMW Cobham, 18-22 Portsmouth Road, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 27 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
COS34 | Oxshott Medical Practice and Village Centre Hall, Holtwood Road | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 11 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Not enough evidence
COS35 | 78 Portsmouth Road, Cobham | Cobham, Oxshott and Stoke D'Abernon | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 30 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Asssessment. The site is considered developable based on the evidence in the urban capacity study. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forwared in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Not enough evidence
D1 | Brook House, Portsmouth Road, Thames Ditton, KT7 0EG | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 30 | [10 empty] | 15 | 15 | [5 empty] | 30 | Typo in draft Plan proposed allocation of 8 units on site. Should have been 30 units. Identified in 2018 Urban Capacity Study [HOU012]. A pre app for change of use from employment floorspace to 49 units was received in early 2024. Council concluded principle of residential development was acceptable subject to the provision of marketing evidence to demonstrate that the site has been unsuccessfully marketed for employment activities for an appropriate period of time. However, a subsequent pre-app was submitted April 2024 for a supermarket use only. Council suggested a mixed use scheme to allow some housing on the site would be more suitable however a mixed use scheme could impact the denisty of housing achievable on the site. Site is considered developable based on the pre-app evidence at 30 units. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forwared in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Developable | 6 to 10 years
D2 | Car Park south of Southbank, Thorkhill Road, Thames Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 7 | [6 empty] | 10 | [10 empty] | 10 | EBC owned site allocated for 7 units in draft Local Plan. EBC AMPS confirmed in May 2024 that intial feasibility work on a scheme of 10 units has been completed with an application to be submitted in the next 12 months. Assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in the early 6 - 10 yr period of the Plan. | Developable | 6 to 10 years
D3 | 4-6 Manor Road South and 4 Greenways, Hinchley Wood | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Allocated for 33 units in draft Local Plan. Site assessment work carried out to inform 2023 Land Availability Assessment concluded that 33 units is not achievable and the site will likely come forward as a windfall devleopment. Application for full PP 2023/2580 for net 3 units under consideration. Submitted Sep. 2023. Decision target date Apr. 2024. | Allocated quantum unachievable. Will fall into windfall.
D4 | Land to the rear of 5 Hinchley Way, Esher, KT10 0BD | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Allocated for 6 units in draft Local Plan. Site is under construction under 2021/1431 for net 6 units, with commencement on site in April 2023. Expect completion 2 yrs after commencement (April 2025) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
D5 | 89-90 Woodfield Road, Thames Ditton, KT7 0DS | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Allocated for 7 units in draft Local Plan. Council review of housing trajectory in support of appeal inquiry of refused application 2023/0962 for Land North of Raleigh Drive, Claygate concluded 7 units is not achieavable and the site will likely come forward as a windfall development. | Allocated quantum unachievable. Will fall into windfall.
D6 | Sundial House, The Molesey Venture, Orchard Lane, East Molesey, KT8 0BN | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 56 |  |  |  |  | 18 | 20 | [11 empty] | 38 | Reduced to 38 units in line with Appeal Decision APP/K3605/W/23/3334391 (Raleigh Drive). Allocated for 61 units in draft Local Plan. Application for full PP 2022/3525 for net 56 units under consideration. Submitted 18 Nov. 2022. Made valid 29 Nov. 2022. Comments due by 26 Oct. 2023. Decision target date 09 Feb. 2024. Decision delayed as flood risk assessment (FRA) needs to be redone due to incorrect data recieved from EA. Results of FRA may require changes to design of scheme and requirement to consult EA on new FRA with a 6 - 8 week wait for their comments. Therefore expect decision in next 6 months - end of 2024. Contacted Agent at Beamish Planning on 15 May 2024 who confirmed applicant is keen to implement asap if granted PP and expect commencement in Q2 2025 (subject to recieving PP), with 18 months to 2.5 yrs to completion (Q2 2027). | Deliverable | 1 to 5 years
D7 | 47 Portsmouth Road, Thames Ditton, KT7 0TA | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Now allocated for retail use. Allocated for 25 units in draft Local Plan. Site was purchased by Aldi in 2020. A mixed use scheme was explored in pre-app with Aldi and officers which concluded harm would result from a residential use. Aldi submitted an application for a supermarket 2021/3857 which was dismissed at appeal in July 2023. However, the application confirmed the site was suitable for commerical use and not residential or mixed use, which the Inspector agreed with in the appeal decision. | No longer available for residential (C3) development
D8 | Torrington, 18-20 St Mary’s Road, Long Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 11 |  |  |  | 11 | [13 empty] | 11 | Allocated for net 9 units in draft Local Plan. Application for full PP 2023/0665 for net 11 units granted at planning committee subject to s106 agreement in Jan. 2024. Contacted agent West Waddy Architects on 15 May 2024 who stated progressing with s106 however discussions with Homes England re funding ongoing. In further discussions on 22 May 2024 confirmed anticipate commencement in early 2025 and completion in spring 2026. | Deliverable | 1 to 5 years
D9 | Corner Cottage, Portsmouth Road, KT7 0TQ | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 5 | [8 empty] | 5 | [8 empty] | 5 | Identified in the LAA from past planning history 2018/3425 - Full PP was refused for 8 flats. It is allocated for 5 units in draft Local Plan. Council received confirmation from landowner that site is available in the 1-5 yr and 6 - 10 yr period of the Plan and has capacity to achieve 6 units in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site considered developable based on the evidence recieved from the landowner but no application or pre-app has been submitted to the Council. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
D10 | Bransby Lodge, St Leonard’s Road, Thames Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 5 | [10 empty] | 5 | [6 empty] | 5 | Identified in the LAA 2022 (HOU002) and LAA 2023 (HOU017) due to planning history with a PP 2020/0865 refused and dismissed at appeal for 9 units gross. It is allocated for 5 units in draft Local Plan. Application for full PP 2023/0794 for 8 units gross 7 net - appeal lodged in April 2024. Reasons for refusal include: 1. Development, by reason of the inadequate and poor quality amenity space for the future occupiers of the development would not result in a suitable residential environment. 2. Development, by reason of the dominance of the buildings and hardstanding as well as the bulk, massing and appearance of the front building, would result in material harm to the character of the street scene and the wider area. 3. Development, by reason of the size, scale and proximity of the frontage building to the front elevations of Nos. 11 - 14 Lynton would result in a material loss of light and outlook which would be materially harmful to the amenity of the occupiers of these properties. 4. Development, by reason of the inclusion of side facing first floor windows which would be the sole windows serving habitable rooms which consequently cannot be obscurely glazed, would result in a material loss of privacy to the occupiers of Nos. 11 to 14 Lynton and Holkham. 5. Development by reason of the overprovision of parking would not contribute towards the Council's key objective of reducing reliance on driving and reducing congestion and pollution caused by traffic. 6. Development by reason of its close proximity and juxtaposition, would lead to foreseeable pressure on the neighbouring trees likely to result in the loss of, or potential harmful pruning of trees that are, or are capable of, making a significant contribution to the character or amenity of the area. 7. Development, by reason of the inadequate biodiversity and ecology information, may result in material harm to on-site biodiversity and ecology. Council considers reasons for refusal can be overcome with a scheme of lower density more in line with the allocated quantum. If an application is recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion by end of 6 - 10 yr period (2033/34). | Developable | 6 to 10 years
D11 | Garages to the rear of Blair Avenue, Weston Green | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Allocated for 4 units in the draft Local Plan. Granted PP under 2020/2566 in May 2023 for net 2 units. No subsequent application submitted. Expect completion 3 yrs after decision date (May 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
D12 | Sandpiper, Newlands Avenue, Thames Ditton, KT7 0HF | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 21 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
D13 | Thames Ditton Centre for the Community, Mercer Close, Thames Ditton, KT7 0BS | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | EBC owned site allocated for reprovision of the existing community use and 18 units in the draft Local Plan. No plans have been developed to date but in May 2024 EBC AMPS confirmed site is developable and could be brought forward for delivery in the 11 - 16 yr period of the Plan. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give time around 10 yrs for a scheme to be developed and 4 yrs to be implemented. Also reflecting the need to reprovide the existing community use which could impact lead in time. | No longer available
D14 | British Legion, Betts Way, Long Ditton, KT6 5HT | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D15 | Flats 9-41 and Garages on Longmead Road, Thames Ditton, KT7 0JF | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D16 | Ashley Road Car Park, Thames Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | EBC owned site allocated for 14 units in the draft Local Plan. Council's Level 2 SFRA identified that the site is unachievable/undeliverable as it cannot accommodate additoinal built footprint. | Not achievable/deliverable due to flood risk issues
D17 | Nuffield Health Club, Simpson Way, Long Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D18 | 118-120 Bridge Road East Molesey KT8 9HW | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D19 | Industrial units at 67 Summer Road East Molesey KT8 9LX | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D20 | School Bungalow, Mercer Close, Thames Ditton, KT7 0BS | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 | SCC owned site allocated in draft Local Plan for 10 units. SCC previously confirmed site could accommodate 2 to 3 plots for housing development adjacent to academy if released. Council received confirmation from SCC that 10 units is not achievable and the site will come forward for 2 - 3 units in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Therefore, site will likely come forward as a windfall development. | Allocated quantum unachievable. Will fall into windfall.
D21 | Nuffield Health car park, Simpson Way, Long Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D22 | 46 St Marys Road, Long Ditton, KT6 5EY | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D23 | Old Pauline Sports Ground Car Park | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not developable
D24 | Community centres at the junction of Mercer Close and Watts Road, Thames Ditton | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 0 | [17 empty] | 0 |  | Not enough evidence
D25 | 5A-6A Station Road, Esher, KT10 8DY | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 5 | [8 empty] | 5 | [8 empty] | 5 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 5 units in draft Local Plan. Council received confirmation from 1 landowner that site is available in the 1 - 5 yr period of the Plan and has capacity to achieve 5 units in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site considered developable based on the evidence in the Urban Capacity Study and response recieved from the landowner but no application or pre-app has been submitted to the Council. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
ESH1 | Esher Place, 30 Esher Place Avenue, Esher, KT10 8PZ | Esher | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 22 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
ESH2 | 30 Copsem Lane, Esher, KT10 9HE | Esher | 25 | [5 empty] | 25 | [11 empty] | 25 | Allocated for 21 units in draft Local Plan. Application for full PP 2021/4149 for net 25 units under consideration. Submitted 02 Dec. 2021. Made valid 18 Jan. 2022. Consultation opened 24 Jan 2024. Decision target date 22 Sep. 2023. Extended consultation, with comments due by 10 April 2024. DM officers advised decision delayed due to outstanding issue relating to highways but applicant is actively working to resolve the issue. Anticipate decision to be issued in next 6 months (Dec. 2024). Contacted agent at Kona Planning on 15 May 2024 who confirmed applicant is looking to deliver the scheme in full within 5 yrs of recieving PP. Anticipate completion by end of the 1 - 5 yr period. | Deliverable | 1 to 5 years
ESH3 | 1-5 Millbourne Lane, Esher, KT10 9DU | Esher | 25 | [14 empty] | 25 |  |  | 25 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 25 units in draft Local Plan. Council received confirmation from 1 of 3 landowners that site is available for development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Landowner confirmed site can be delivered in the 6 - 10 yr period of the Plan. No planning application or pre-app submitted to Council to date. Given evidence in the urban capacity study and response from landowner the site is considered developable. The site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short. However, as 2 of the 3 landowners have not responsed delivery in the 11 - 16 yr period of the Plan more realistic giving around 10 years for a scheme to be worked up and submitted and 4 yrs for determination and completion. | Developable | 11 to 15 years
ESH4 | Hanover Cottage 6 Claremont Lane Esher KT10 9DW | Esher | 12 | [13 empty] | 12 |  |  |  | 12 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 12 units in draft Local Plan. Council received confirmation from landowner that site is available in the 11 - 15 yr period of the Plan in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment but no pre-app or application has been submitted. As the site is a small major development of less than 20 units and could be built out relatively quickly. However, the Council considers 11 - 16 yr period more realistic in light of correspondence from Landowner. Anticipate delivery from 2036/37 giving around 10 years to work up a scheme and 4 years for determination and completion. | Developable | 11 to 15 years
ESH5 | 35 New Road, Esher, KT10 9DW | Esher | 0 | [17 empty] | 0 | Allocated for 5 units in draft Local Plan. Application for full PP 2023/2776 for 4 units refused in Sep. 2023. Full PP granted under 2023/0302 for net 3 units in Jan. 2024. Applicant progressing with discharge of conditions under 2024/1081 submitted in Apr. 2024. Expect completion 3 yrs after decision date (Jan. 2027) in line with average build out rates for sites of 1 - 9 units in the Borough. Site considered deliverable but falls into windfall category. | Deliverable but less than allocated and falls into windfall category. | 1 to 5 years
ESH6 | 6 Bracondale and 43 Claremont Lane, KT10 9EN | Esher | 0 | [17 empty] | 0 | Identified through pre-app discussion between landowners and Council on scheme of 34 units in 2019. Council concluded principle of development is acceptable. No further pre-apps or application has been submitted. The site is considered developable based on the pre-app evidence. However, Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study and no application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Not enough evidence
ESH7 | Willow House, Mayfair House and Amberhurst, Claremont Lane, Esher, KT10 9DW | Esher | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 57 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
ESH8 | Highwaymans Cottage Car Park, Portsmouth Road, Esher | Esher | 0 | [17 empty] | 0 | EBC owned site allocated for 9 units in draft Local Plan. EBC AMPS confirmed in May 2024 that the intital feasibility study concluded due to restrictive covenants requires the land to remain in use as a car park the site is no longer available for development. | No longer available | 11 to 15 years
ESH9 | Cafe Rouge, Portsmouth Road, Esher, KT10 9AD | Esher | 20 | [9 empty] | 20 | [7 empty] | 20 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 20 units in draft Local Plan. Council received confirmation from landowner that site is available for development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. However, two applications were withdrawn in 2021 and 2022 and since no pre-app or subsequent application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33 - 2033/34. | Developable | 6 to 10 years
ESH10 | 40 New Road, Esher, KT10 9NU | Esher | 5 | [5 empty] | 5 | [11 empty] | 5 | Allocated for 6 units in draft Local Plan. Application for full PP 2022/2086 for net 8 units refused in Oct. 2023. Appeal lodged with PINS in Mar. 2024. Officer recommendation for grant of permission. However, Council decided to refuse PP. Reasons for refusal include: 1. Development would be out of keeping with the character of the street and the wider area due to cramped layout and back-land-location. 2. Development would not offer suitable amenity space for future occupiers. 3. Development would result in a material loss of outlook from No. 42 New Road and No. 2 Broomfields. 4. Development would lead to future pressure for the removal of the trees which would be detrimental to the character and amenity of the area. 5. Applicant hasn't demonstrated how a measurable biodiversity net gain. 6. Development would not reflect the prevailing character of New Road would be provided on-site. 7. Proposed parking provision would not be appropriate to the development and would foreseeably result in on-street parking. Council has suubmitted it's statement of case. Expect decision on appeal within the next 3 - 4 months, at the Inspector's discretion. Subsequent application for full PP 2024/0243 for net 5 units more closely aligned with the quantum in the site allocation Submitted in Jan. 2024. Decision target date 16 Jun. 2024. Anticipate commencement 1 yr after decision date (Jun. 2025) with completion 3 yrs after decision date (from Jun. 2027) in line with average build out rates for schemes of 1 - 9 units in the Borough. Therefore could see completion by the end of the 1 - 5 yr period. | Deliverable | 1 to 5 years
ESH11 | 45 More Lane, Esher, KT10 8AP | Esher | 0 | [17 empty] | 0 | Site allocation ESH11 allocated for 25 units in draft Local Plan. S73 application for variation of condition 2 approved plans of 2021/1791 granted PP under 2022/2392 in Feb. 2023. Second S73 for variation of condition 2 approved plans of 2022/2392 granted PP under 2022/2392 in Dec. 2023. Discharge of all pre-commencement conditions of PP 2021/1791 under 2022/2691 confirmed in Nov 2023. Officers confirmed work on site is underway with commencement notice expected in the 3 - 6 months. Contacted developer Octagon Housing on 17 May 2024 who confirmed anticipate completion in Aug./Sep. 2024. | Deliverable | 1 to 5 years
ESH12 | Garages at Farm Road, Esher, KT10 8AX | Esher | 0 | [17 empty] | 0 | PA Housing site allocated for 3 units in the draft Local Plan. No pre-app or application has been submitted to the Council and the site is therefore not considered deliverable in the first 3 yrs of the Plan period. The site is considered developable but will likely come forward as windfall development. | Developable but will fall into windfall category. | 1 to 5 years
ESH13 | 42 New Road Esher KT10 9NU | Esher | 6 | [6 empty] | 6 | [10 empty] | 6 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 6 units in the draft Local Plan. Landowner confirmed the site is available for development in response to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The landowner indicating that development could come forward in the 1 - 5 yr period of the Plan. Site considered developable based on the evidence in the Urban Capacity Study and response from the landowner but no application or pre-app has been submitted to the Council. Anticipate PP recieved in 1 - 5 yr period although landowner indicated site could be deliverable an application/pre-app has not been submitted to date. Therefore anticipate completion in the early part of the 6 - 10 yr period. Giving 2 yrs for a application to be worked up, submitted and determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
ESH14 | Two Furlongs and Wren House, Portsmouth Road, Esher, KT10 9AA | Esher | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 10 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2029/30. | Not enough evidence
ESH15 | Unit A & B Sandown Industrial Park, Esher, KT10 8BL | Esher | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 40 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
ESH16 | River Mole Business Park, Mill Road, Esher, KT10 8BJ | Esher | 200 | [6 empty] | 49 | 49 | 49 | 49 | 4 | [6 empty] | 200 | EBC owned site allocated for 200 units in draft Local Plan. In May 2024 EBC AMPS and Regeneration confirmed they are actively working to bring site forward for delivery in the 6 - 10 yr period of Plan. Viability and feasibility studies have been undertaken on development options for the site, with quantums of 160 - 240 units (200 units representing the mid point). Programme of work includes public consultations on identified options in early 2025 and selection of preferred option in July 2025, with work on a planning application to follow for submission in late 2025/early 2026. Anticipate PP is received in 2 yrs from submission (late 2027/early 2028), with first completions 2 yrs later (2029/2030) and an average build out rate of 49 dpa from Lichfields Start to Finish (Third Edition) for scheme of 100 - 499 units. Extent not correct. Incorrectly drawn based on EBC land ownership. | Developable | 6 to 10 years
ESH17 | Units C and D, Sandown Industrial Park, Mill Road, Esher | Esher | 60 | [6 empty] | 20 | 20 | 20 | [8 empty] | 60 | EBC owned site allocated for 60 units in draft Local Plan. In May 2024 EBC AMPS and Regeneration confirmed they are actively working to bring site forward for delivery in 6 - 10 yr period of Plan. Viability and feasibility studies have been undertaken on development options for the site, with quantums of 87 units (67 apartments and 20 houses). Programme of work includes public consultations on identified options in early 2025 and selection of preferred option in July 2025, with work on a planning application to follow for submission in late 2025/early 2026. Anticipate PP is received in 2 yrs from submission (late 2027/early 2028), with first completions 2.5 yrs later (2029/2030) and an average build out rate of 20 dpa from Lichfields Start to Finish (Third Edition) for scheme of 50 - 99 units. | Developable | 6 to 10 years
ESH18 | Windsor House 34-40 High Street | Esher | 8 | [8 empty] | 8 | [8 empty] | 8 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council received a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study for 6-10 years. Site considered developable based on the evidence in the Urban Capacity Study and landowner confirmation but no application or pre-app has been submitted to the Council. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
ESH19 | Hawkshill Place Portsmouth Road Esher KT10 9HY | Esher | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 12 units. Council received confirmation from landowners that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
ESH20 | 81 High Street, Esher, KT10 9QA | Esher | 0 | [17 empty] | 0 | EBC owned site allocated for 8 units in draft Local Plan. EBC AMPS confirmed that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
ESH21 | Esher Library and land adjoining, Church Street, Esher, KT10 9NS | Esher | 15 | [9 empty] | 15 | [7 empty] | 15 | EBC owned site leased by SCC allocated reprovision of the existing community use and 15 units in the draft Local Plan. SCC confirmed in response to the Regulation 19 consultation that the library use would be retained but also that they may consider redevleopment of the site including reprovision of the library and an element of residential subject to feasibility studies and options appraisal. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33 - 2033/34. | Developable | 6 to 10 years
ESH22 | 15 Clare Hill Esher KT10 9NB | Esher | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 55 units in draft Local Plan. Council didn't receive confirmation of availability in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted to the Council to date. As the site is a larger major development (50 - 99 units) and the lead in times can be a bit longer the Council anticipates the site could come forwared in the 11 - 16 yr period of the Plan. Using Lichfields Start to Finish (Third Edition) average time for sites of 50 - 99 units of 1.5 yrs to go from validation of an application to decision and 2.5 yrs from decision to first completions with an average build out rate of 20 dpa. If PP were submitted and approved in the 6 - 10 year period. Could anticipate first completions from 2036/2037. | Not enough evidence
ESH23 | St Andrews and Hillbrow House, Portsmouth Road, Esher, KT10 9SA | Esher | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but was not considered deliverable as would require conversion from commerical use to residential. However, PD rights now allow this change of us without PP. As such, Council considers the site to be deliverable and allocated it for 30 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Asssessment. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Not enough evidence
ESH24 | Civic Centre, High Street, Esher | Esher | 400 | [8 empty] | 8 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 400 | EBC owned site allocated for mixed use including 400 units in the draft Local Plan. Note that typo in draft Plan meant it didn't identify the mixed use element. Feasibility work undertaken by the Council found 400 units is achievable as a 4 storey building of 1 and 2 bed flats. Heritage asset Sandown House considered in feasibility/capacity work. Council has also undertaken transport capacity work to support the 400 unit scheme. EBC AMPS confirmed in May 2024 that they are working to procure a developer/architect to undertake masterplanning within the next 12 months and anticipate commencement on site within 5 yrs (2028/29) and first completions 3 to 4 yrs after (2031/32 - 2032/33). Apply average build out rate of around 49 dpa from Lichfields Start to Finish (Third Edition) for schemes of 100 - 499 units. | Developable | 11 to 15 years
H1 | 63 Queens Road, Hersham, KT12 5LA | Hersham | 5 | [10 empty] | 5 | [6 empty] | 5 | Allocated for 5 units and retention of existing community use in draft Plan. Application for full PP 2019/1320 for 7 Flats refused in Dec. 2019. Reaons for refusal include: 1. development would result in the loss of community use which would not be replaced by equivalent or better provision at the site nor is there any justification that there would be alternative community use in a suitable location in the locality. 2. The scheme, due to its form, materials, scale and proportions would provide a jarring visual appearance detrimental to the character and appearance of the area appearing discordant and incongruous. 3. Proposal would, by reason of the lack of a satisfactory completed Unilateral Undertaking in relation to the provision of affordable housing. Two subsequent Lawful Development Certificates for change of use from community use to office 2022/0301 dismissed at appeal in Mar. 2023 and 2022/1618 refused in July 2022. Refused application was not in accordance with the allocation due to loss of community use and proposed a devleopment of greater density. The Council considers the reasons for refusal can be overcome if the density is reduced and the community use retained in accordance with the draft Local Plan allocation. Site is therefore considered developable. If a subsequent application is recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion by the end of the 6 - 10 yr period from 2033/32. | Developable | 6 to 10 years
H2 | 19 Old Esher Road, Hersham, KT12 4LA | Hersham | 0 | [17 empty] | 0 | Allocated for 5 units in draft Local Plan. Council review of housing trajectory in support of appeal inquiry of refused application 2023/0962 for Land North of Raleigh Drive, Claygate concluded 5 units is not achieavable and the site will likely come forward as a windfall development. | Allocated quantum unachievable. Will fall into windfall.
H3 | Hersham Shopping Centre, Molesey Road, Hersham | Hersham | 100 | [6 empty] | 49 | 49 | 2 | [8 empty] | 100 | Allocated for 200 units in draft Local Plan. Site was orginally identified in the 2018 Urban Capacity Study [HOU012] but only the Waitrose car park and EBC car park components of the site were being considered for consolidation to allow a small site for housing. The landowners at that time, confirmed interest in developing Waitrose car park site in 2020. Since then, new applicants began considering a redevelopment of the whole Shopping Centre and submitted a PPA in 2021. Following Applicant's capacity work, PPA with the Council and consultation with the local community, applicant has confirmed 200 units is not achievable with 100 units now considered an achievable and deliverable quantum. A hybrid planning application (2024/0498) was submitted in April 2024 and is currently under consideration. Latest discussions confirm plans to deliver site in the 6 - 10 yr period of the Plan. Anticipate grant of PP, reserved matters and discharge of conditions within 3 yrs, commencement from 2026/27 and first completions from 2029/30. Apply average build out rate of 49 dpa from Lichfields Start to Finish (second edition) for schemes of 100 - 499 units. | Developable | 6 to 10 years
H4 | Park House, Pratts Lane, Hersham, KT12 4RR | Hersham | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 5 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
H5 | Car park to the south of Mayfield Road, Hersham | Hersham | 9 | [15 empty] | 9 |  | 9 | EBC owned site allocated for 9 units in the draft Local Plan. No plans have been developed yet but EBC AMPS confirmed site to be brought forward for delivery in the 11 - 15 yr period of the Plan in May 2024. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give around 10 yrs for a scheme to be developed and 4 yrs to be implemented. | Developable | 11 to 15 years
H6 | Hersham Day Centre and Village Hall, Queens Road, Hersham, KT12- 5LU | Hersham | 15 | [16 empty] | 15 | 15 | EBC owned site allocated for mixed use, including 15 units in the draft Local Plan. EBC AMPS confirmed in May 2024 that no plans have been developed and the village hall has been leased for a 5 yr period. However, EBC AMPS indicated that beyond the 5 yr lease the site can still be considered for development. Delivery pushed back to end of the 11 - 16 yr period to give ample time for a scheme to be developed afetr the 5 yr lease is up. | Developable | 11 to 15 years
H7 | New Berry Lane car park, Hersham | Hersham | 0 | [17 empty] | 0 | EBC owned site allocated for 7 units in the draft Local Plan. EBC AMPS confirmed in May 2024 that in light of resident response the site is no longer available for development and will be retained as a car park. | No longer available
H8 | Hersham sports and social club 128 Hersham Road Hersham KT12 5QL | Hersham | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 8 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
H9 | Volkswagen Ltd Esher Road Hersham KT12 4JY | Hersham | 0 | [17 empty] | 0 |  | Not enough evidence
H10 | The Royal George 130-132 Hersham Road Hersham KT12 5QJ | Hersham | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 15 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
H11 | Trinity Hall and 63-67 Molesey Road, Hersham | Hersham | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012]and allocated for 47 units in draft Local Plan. However, due to the presence of a Grade II listed building - The Barley Mow Public House and a sewage pumping station in the centre of the site. It is no longer considered developable. | No longer available
H12 | Car Park next to Waterloo Court | Hersham | 62 | [10 empty] | 28 | [6 empty] | 28 | Network Rail owned site identified in the 2018 Urban Capacity Study and allocated for 62 units in draft Local Plan. In a land disposal evaluation dated Feb. 2021 Network Rail confirmed intention to dispose of site and transfer it to Solumn Regeneration for housing development. The proposed development is 26 units and is anticipated to come forward for PP in spring 2025, with commencement in early 2026 and completion by the end of 2026. Solumn entered pre-app discussions with the Council in November 2023 for a scheme of 28 terraced houses. Pre-app is still under consideration. Delivery pushed back to end of 6 - 10 yr period (2033/34) to reflect that pre-app discussion not closed and need to submit application, around 1 yr for decision, 2.5 yrs to commencement and 3 yrs from commencement to completion from decsion in line with the average build out rates for schemes of 10 - 49 units in the Borough. | Developable | 6 to 10 years
H13 | All Saints Catholic Church hall Queens Road Hersham KT12 5LU | Hersham | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. Site considered developable based on the evidence in the Urban Capacity Study but no application or pre-app has been submitted to the Council. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
H14 | Hersham Technology Park (Air Products) | Hersham | 0 | [17 empty] | 0 | Employment floorspace allocation. | Developable | 11 to 15 years
H15 | Hersham Library, Molesey Road, Hersham, KT12 4RF | Hersham | 13 | [16 empty] | 13 | 13 | SCC owned site allocated for reprovision of the library and 13 units in draft Local Plan. In response to the Regulation 19 consultation SCC confirmed that the library use would be retained but also that they may consider redevleopment of the site including reprovision of the library and an element of residential subject to feasibility studies and options appraisal. Delivery pushed back to end of 11 - 16 yr period to reflect uncertainty around delivery of site and potential for longer lead in times as scheme may be more complex due to the need to retain the exisiting library. | Developable | 11 to 15 years
MOL1 | 2 Beauchamp Road, East Molesey, KT8 0PA | Molesey | 0 | [17 empty] | 0 | Allocated for 9 units in draft Local Plan. Council review of housing trajectory in support of appeal inquiry of refused application 2023/0962 for Land North of Raleigh Drive, Claygate concluded 9 units is not achieavable and the site will likely come forward as a windfall development. | Allocated quantum unachievable. Will fall into windfall.
MOL2 | 133-135 Walton Road, East Molesey, KT8 0DT | Molesey | 8 | [8 empty] | 8 | [8 empty] | 8 | Site identified through pre-app discussions between landowners and Council on scheme comprising 2 commercial units at ground floor with 8 residential units above. Council concluded principle of development is acceptable. Landowners confirmed site is deliverable in 1 - 5 yr period of Plan in the LAA 2023 land ownership checks. However, no application submitted to date. Given pre-app evidence site is considered developable in the 6 - 10 yr period. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
MOL 3 | Garage block west of 14 and north of 15 Brende Gardens, West Molesey | Molesey | 0 | [17 empty] | 0 | PA Housing site allocated for 2 units in draft Local Plan (4 units in submitted Plan). Application for full PP 2021/0345 for 2 units submitted in Feb. 2021 under consideration. Made valid in Feb. 2021 and comments due by April 2021. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Deliverable but will fall into windfall category. | 1 to 5 years
MOL4 | East Molesey Car Park, Walton Road, East Molesey | Molesey | 0 | [17 empty] | 0 | EBC owned site allocated in draft Local Plan for 23 units. EBC AMPS confirmed site is no longer available for housing development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is now proposed for use as a medical centre. | Not available for housing (C3) development
MOL5 | Garages to the rear of Belvedere Gardens, West Molesey | Molesey | 0 | [17 empty] | 0 | Allocated for 4 units in draft Local Plan. Granted PP under 2020/3003 in Mar. 2023 for net 4 units. No subsequent application submitted. Expect completion 3 yrs after decision date (Mar. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
MOL6 | Garages to the rear of Island Farm Road, West Molesey | Molesey | 0 | [17 empty] | 0 | PA Housing site allocated for 3 units in draft Local Plan. Application for full PP 2020/3004 for 3 units submitted in Nov. 2020 under consideration. Made valid in Nov. 2020 and comments due by Dec. 2023. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Deliverable but will fall into windfall category. | 1 to 5 years
MOL8 | 7 Seymour Close and Land to rear of 103-113 Seymour Close, East Molesey, KT8 0JY | Molesey | [18 empty] | 0 | Identified in LAA 2022 and LAA 2023 through past planning history (2017/3711) and a subsequent pre-application received in 2018 for 7 units. It is allocated for 5 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the past planning history and pre-app. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
MOL9 | 11-27 Down Street, West Molesey, KT8 2TG | Molesey | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and in a 2018 pre-app for a number of garage sites across the Borough, the site has been allocated for 7 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study and the landowner PA Housing's intention to develop garage sites across the Borough. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
MOL10 | Vine Medical Centre 69 Pemberton Road East Molesey KT8 9LJ | Molesey | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 7 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
MOL11 | Molesey Hospital, High Street, KT8 2LU | Molesey | 70 | [13 empty] | 10 | 20 | 20 | 20 | 70 | Identified in 2018 Urban Capacity Study [HOU012] and allocated 70 units in draft Local Plan. Availability and capacity confirmed in Regulation 19 representation from landowner who confirmed site is deliverable in the 6 - 10 yr period of the Plan (Rep ID #1112162). Site is considered developable based on the evidence in the urban capacity study and information submitted by the landowner at Regulation 19. However, no pre-app or application has been submitted to the Council to date. Although the landowner has indicated site could come forward in the 6 - 10 yr period. As the site is a larger major development (50 - 99 units) and the lead in times can be a bit longer and no pre-app has been submitted. The Council anticipates the site to come forwared in the 11 - 16 yr period of the Plan. Using Lichfields Start to Finish (Third Edition) average time for sites of 50 - 99 units of 1.5 yrs to go from validation of an application to decision and 2.5 yrs from decision to first completions with an average build out rate of 20 dpa. If PP were submitted and approved in the 6 - 10 year period. Could anticipate first completions from 2036/37. | Developable | 11 to 15 years
MOL12 | Henrietta Parker Centre, Ray Road, West Molesey | Molesey | 13 | [16 empty] | 13 | 13 | SCC owned site allocated for 13 units in draft Local Plan. Council received confirmation from SCC that site is developable at the quantum identified in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. No plans have been developed yet but SCC confirmed site to be brought forward in the 11 - 15 yr period of the draft Local Plan. Delivery anticipate in the back end of the 11 - 16 yr period reflecting SCC's response, giving around 10 years for a scheme to be worked up and submitted, and 4 yrs for determination and implementation. | Developable | 11 to 15 years
MOL13 | Parking/garages at Grove Court Walton Road East Molesey KT8 0DG | Molesey | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 7 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted, Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
MOL14 | 43 Palace Road East Molesey KT8 9DN | Molesey | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 18 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
MOL15 | Pavilion Sports Club car park Hurst Lane East Molesey KT8 9DX | Molesey | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 9 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
MOL16 | Tesco Metro car park, Walton Road, East Molesey | Molesey | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 11 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
MOL17 | Water Works south of Hurst Road, West Molesey | Molesey | 0 | [17 empty] | 0 | Thames Water owned site identified in 2018 Urban Capacity Study [HOU012] and allocated for 14 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The Council followed up in May 2024 when Thames Water confirmed the site is operational and not available for development. | No longer available
MOL18 | Molesey Clinic and library, Walton Road, West Molesey, KT8 2HZ | Molesey | 0 | [17 empty] | 0 | SCC owned site allocated in draft Local Plan for 10 units. Council received confirmation from SCC that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. The site has been transfered to NHS ownership who are not intending to release it for development. | No longer available
MOL19 | 5 Matham Road East Molesey KT8 0SX | Molesey | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 23 units in draft Local Plan. Whilst the urban capacity study discounted the site due to viability constraints associated with replacement of an existing dwelling on the site. The Council considers the site is developable in the 11 - 15 yr period of the Plan if a sensitive conversion of the existing dwelling were part of the proposal. This gives time for a scheme to be worked up and submitted. No pre-app or application has been submitted to the Council. Although the site is relatively small (20 - 49 units). Longer lead in times are anticipated due to the need for a sensitive conversation which could result a longer period working up an application and more conditions to discharge. Therefore delivery in the back end of the 11 - 16 year period is considered more realistic. | Not enough evidence
MOL20 | Joseph Palmer Centre, 319a Walton Road | Molesey | 30 | [13 empty] | 15 | 15 |  |  | 30 | SCC owned site allocated for 60 C2 units (30 at 0.5 rate) in draft Local Plan. In response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment SCC confirmed that no plans have been developed yet but reiterated site is to be brought forward for housing development with delivery in the 11 - 15 yr period of the draft Plan. Using Lichfields Start to Finish (Third Edition) average time for sites of 50 - 99 units of 1.5 yrs to go from validation of an application to decision and 2.5 yrs from decision to first completions with an average build out rate of 20 dpa. If PP were submitted and approved in the 6 - 10 year period. Could anticipate first completions from 2036/37. | Developable | 11 to 15 years
WOT1 | 12-16a High Street, Walton-on-Thames, KT12 1DA | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated for 24 units in draft Local Plan. Application for full PP 2023/3378 for mixed use C3 and flexible Class E floorspace with 0 net gain of homes. Submitted Dec. 2023. Made valid Dec. 2023. Decision target date Mar. 2024. | No longer available for residential (C3) development
WOT2 | Leylands House, Molesey Road, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated for 56 units in draft Local Plan. Landowner confirmed in Reg. 19 representation that site is no longer available. | No longer available
WOT3 | Garages to the rear of 84-92and 94-96 Rodney Road, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | PA Housing site allocated for 1 units in draft Local Plan. Application for full PP 2020/3450 for 1 units submitted in Dec. 2020 under consideration. Made valid in Jan. 2021 and comments due by March 2023. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Deliverable but will fall into windfall category. | 1 to 5 years
WOT4 | 9-21a High Street, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Site allocation WOT4 allocated for 71 units and commercial floorspace in draft Local Plan. No subsequent application submitted. Discharge of precommencement conditions required. Including 3 (Materials samples), 5 (Asbestos Containing Materials), 6 (Noise Insulation), 11 (SuDS), 13 (Sensitive Lighting Management Plan), 14 (Ecological Enhancement Plan), 18 (Construction Transport Management Plan), 20 (Potential Contaminated Land). No progress to date. Contacted agent at Barton Willmore on 17 May 2024 who confirmed work is progressing with applications for discharge of conditions. They anticipate commencement of AH component of scheme in 2 yrs (May 2026) and first completions in 3 - 4 yrs (May 2027 - 2028). Expected further detail on build out rate from developer but not recieved. Apply average build out rate of 20 dpa for sites of 50 - 99 units from Lichfields Start to Finish (Third Edition). | Deliverable | 1 to 5 years
WOT5 | 63-69 High Street, Walton-on-Thames, KT12 1DJ | Walton-on-Thames | 28 | [14 empty] | 28 |  |  | 28 | Identified through a pre-app submitted in 2019 for a mixed use scheme including 29 units. Council recommended that the principle of a mixed use scheme and intensification of the residential use on the site could be acceptable subject to the scheme demonstrating that the commercial uses are suitably flexible; provision of onsite affordable housing; and exploring the possible provision of 3 bed family units. The site was allocated for 28 units in draft Local Plan. Council received confirmation from landowners that site is available for development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Landowners confirmed site can be delivered in the 11 - 15 yr period of the Plan. The site is considered developable based on the pre-application and ownership confirmation. However, no planning application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short. However, as the landowner has signaled the site is deliverable in the 11 - 16 yr period of the Plan the Council has reflected this, with delivery anticipated from 2037/38 giving around 10 years for a scheme to be worked up and submitted and 4 yrs for determination and implementation. | Developable | 6 to 10 years
WOT6 | Garages to the rear of 17-27 Field Common Lane Walton-On-Thames KT12 3QH | Walton-on-Thames | 0 | [17 empty] | 0 | PA Housing owned site allocated for 3 units in draft Local Plan. Application for full PP 2023/2955 for net 3 units under consideration. Submitted 30 Oct. 2023. Made valid 28 Oct. 2023. Comments due by 29 Dec. 2023. Decision target date 23 Jan. 2024. Decision delayed due to outstanding issues raised by SCC Highways and Joint Waste Solutions. Expect to take to committe and issue decision in next 6 months (Dec. 2024). Expect completion in 3 yrs after decision (Dec. 2027) and wil therefore fall under windfall. | Deliverable but will fall into windfall category. | 1 to 5 years
WOT7 | Walton Park Car Park, Walton Park, KT12 3ET | Walton-on-Thames | 17 | [9 empty] | 17 | [7 empty] | 17 | EBC owned site allocated for 17 units in draft Local Plan in May 2024 EBC AMPS confirmed feasibility work has been undertaken confirming a scheme of 17 units is deliverable on the site. Council aiming to move forward with options appraisal and consultation with application planned within the next 5 years. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Developable | 6 to 10 years
WOT8 | 16-18 Sandy Lane, KT10 9PG | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated for 7 units in draft Local Plan. Site is under construction under 2022/1998 and 2021/2764 for net 5 units, with commencement on site in Oct. 2022. Discharge of condition 3 (Material Samples), 6 (Electric Vehicle Charging), 7 (Construction Transport Management Plan) and 8 (Potential Land Contamination) of 2021/2764 under 2022/2040 confirmed in Sep. 2022; conditon 6 (Electric vehicle charging) 7 (Construction management plan) 8 (Potential land contamination) and 9 (Landscaping scheme) of 2022/1998 under 2022/3745 confirmed in part / refused in part in Mar. 2023. S73 application for variation of Condition 2 (Approved plans) of 2022/1998 granted in Mar. 2023. NMA to PP 2022/3688 granted in May 2024. Deed of variation to remove the Early and Late Review Mechanism for Viability from PP 2022/2388 submitted April 2024. Decision target date Jun. 2024. Expect completion 2 yrs after commencement (Oct. 2024) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
WOT9 | Garages adjacent to 1 Tumbling Bay Walton-On-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | PA Housing site allocated for 2 units in draft Local Plan. No application submitted to date. Pre-application submitted in 2021 providing two options for the site. Prinicple of residential development supported. It is expected to come forward in years 6 - 10. As less than 5 units the site would fall into windfall development. | Developable but will fall into windfall category. | 6 to 10 years
WOT10 | Garages at Sunnyside, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | PA Housing site allocated for 4 units in draft Local Plan. Application for full PP 2022/1271 for 4 units submitted in April. 2022 under consideration. Made valid in April. 2022 and comments due by Oct. 2023. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Developable but will fall into windfall category. | 6 to 10 years
WOT11 | The Playhouse, Hurst Grove, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | EBC owned site allocated in draft Local Plan for 20 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WOT12 | 147 Sidney Road, KT12 3SA | Walton-on-Thames | 0 | [17 empty] | 0 | Identified through 2021 pre-app and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming avaialbility for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the pre-app evidence but no application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT13 | Halfway Car Park, Hersham Road, Walton-on-Thames | Walton-on-Thames | 8 | [15 empty] | 8 |  | 8 | EBC owned site allocated for 8 units in the draft Local Plan. No plans have been developed yet but EBC AMPS confirmed in May 2024 site to be brought forward for delivery in the 11 - 15 yr period of the Plan. Delivery pushed back to end of Plan period (2038/39 - 2039/40) period to give around 10 yrs for a scheme to be developed and 4 yrs to be implemented. | Developable | 11 to 15 years
WOT14 | 20 Sandy Lane, Walton-on-Thames, KT12 2EQ | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but considered not able to accommodate 5 units or more. However, Council allocated it for 7 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study and no pre-app or application. If development were to come forward on the site it would likely be for less than 5 units and would fall into windfall. | Developable but will fall into windfall category. | 6 to 10 years
WOT15 | Bradshaw House Bishops Hill and Walton Centre for the Community, Manor Road, Walton-On-Thames KT12 2PB | Walton-on-Thames | 18 | [16 empty] | 18 | 18 | EBC owned site allocated for net 18 units in draft Local Plan. In May 2024 EBC AMPS confirmed no plans have been developed and there are no short terms plans to do so. However, they confirmed the site is developable and will be considered within the next 10 years. Delivery pushed back to end of the 11 - 16 yr period of the plan to reflect uncertainty and potential for scheme to come forward in next 10 years. | Developable | 11 to 15 years
WOT16 | Elm Grove, 1 Hersham Road, Walton-on-Thames, KT12 1LH | Walton-on-Thames | 70 | [13 empty] | 10 | 20 | 20 | 20 | 70 | EBC owned site allocated for a medical centre use and 70 units resulting from a land swap in the draft Local Plan. No plans for the residential development have been developed yet but EBC AMPS confirmed in May 2024 that they are bringing forward an application for the medical centre use in the next 12 months with work on the land swap and residential scheme to follow. Using Lichfields Start to Finish (Third Edition) average time for sites of 50 - 99 units of 1.5 yrs to go from validation of an application to decision and 2.5 yrs from decision to first completions with an average build out rate of 22 dpa. If PP were submitted and approved in the 6 - 10 year period. Could anticipate first completions from 2036/2037. | Developable | 11 to 15 years
WOT17 | Rylton House, Hersham Road, Walton-On-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT18 | Cornerstone Church, 38 Station Avenue, Walton- On-Thames, KT12 1NU | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] however, the site was not considered to be deliverable due to the presence of a community use. The Council considered the community use can be reprovided on site and allocated it for reprovision of the use and 30 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Assessment and no pre-app or application has been submitted to the Council. Although the site is relatively small (20 - 49 units). Longer lead in times are anticipated due to the need a scheme including the reprovision of the existing community use, which could result a longer period working up an application and more conditions to discharge. Therefore delivery in the back end of the 11 - 16 year period is considered more realistic. | Not enough evidence
WOT19 | Walton Comrades Club 7 Franklyn Road Walton-On-Thames KT12 2LF | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 16 units. Council received confirmation from sole landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WOT20 | P G S Court, Halfway Green, Walton-on-Thames, KT12 1FJ | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 23 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. The site is considered developable based on the evidence in the urban capacity study. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Not enough evidence
WOT21 | Fire/Ambulance station Hersham Road Walton-On-Thames KT12 1RZ | Walton-on-Thames | 0 | [17 empty] | 0 | SCC owned site allocated in draft Local Plan for 21 units. Council received confirmation from SCC that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is operational as a fire/ambulance station and they no longer have any plans to release it for development. | No longer available
WOT22 | Land to the rear of 60-70 Sandy Lane, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT23 | Unit Rear of and 12-14 Sandy Lane Walton-On-Thames KT12 2EQ | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 9 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT24 | Garages off Copenhagen Way, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 7 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WOT25 | Regnolruf Court, Church Street, Walton-on-Thames, KT12 2QT | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated for 7 units in the draft Local Plan through the provision of an additional storey on the existing building on the site. A pre-app enquiry was received in 2014 for such a scheme. Council did not raise an objection to the principle of development as identified in the allocation but an application has not been submitted. The site is considered developable based on the pre-app evidence but an application has not been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
WOT26 | Fernleigh Day Centre Fernleigh Close Walton-On-Thames KT12 1RD | Walton-on-Thames | 0 | [17 empty] | 0 | SCC owned site allocated for 19 units in draft Local Plan. Council received confirmation from SCC that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is operational in day centre use and they no longer have any plans to release it for development. | No longer available
WOT27 | Garages to the rear of 8 Sidney Road, Walton-on- Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT28 | Garages at Collingwood Place, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 9 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WOT29 | Garages at Home Farm Gardens, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 6 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT30 | Case House 85-89 High Street Walton On Thames KT12 1DZ | Walton-on-Thames | 0 | [17 empty] | 0 | PA Housing site identified in 2018 Urban Capacity Study [HOU012] and allocated for 28 units in draft Local Plan. Council didn’t receive a response from the landowner in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. The site is considered developable based on the evidence in the urban capacity study. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 20 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Not enough evidence
WOT31 | Station Avenue Car Park, Station Avenue, Walton-on-Thames | Walton-on-Thames | 0 | [17 empty] | 0 | EBC owned site allocated in draft Local Plan for 50 units. EBC AMPS confirmed that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WOT32 | 1 Cleveland Close Walton-On-Thames KT12 1RB | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but was not considered to be deliverable due to multiple landowners and existing commercial. The Council considered the site to be developable but requiring the applicant to demonstrate the existing use can be reolocated and allocated for 8 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WOT33 | Manor Road Car Park, Manor Road, Walton-on-Thames, KT12 2QN | Walton-on-Thames | 31 | [15 empty] | 15 | 16 | 31 | EBC owned site allocated for 37 units in draft Local Plan. No plans have been developed yet but EBC AMPS confirmed in May 2024 that site is developable and can be brought forward for delivery in the 11 - 16 yr period of the Plan in May 2024. Anticipate delivery in the back end of the 11 - 16 yr period giving around 10 yrs for a scheme to be worked up and submitted and 4 yrs for determination and implementation. | Developable | 11 to 15 years
WOT34 | Courtlands & 1-5 Terrace Road, Walton-on-Thames | Walton-on-Thames | [18 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but was not considered to be deliverable due to the existing retail use. The Council considered the site to be developable through a mixed use redevelopment that keeps the existing retail use and allocated it for 63 units in draft Local Plan. Council didn't receive confirmation of availability in response to the land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Site is considered developable based on the evidence in the urban capacity study. No pre-app or application has been submitted to the Council to date. As the site is a larger major development (50 - 99 units) and the lead in times can be a bit longer the Council cautiously anticipates the site to come forward in the 11 - 16 yr period of the Plan. Using Lichfields Start to Finish (Third Edition) average time for sites of 50 - 99 units of 1.5 yrs to go from validation of an application to decision and 2.5 yrs from decision to first completions with an average build out rate of 20 dpa. If PP were submitted and approved in the 6 - 10 year period. Could anticipate first completions from 2036/2037. | Not enough evidence
WOT35 | The Heath Centre, Rodney Road, Walton-on-Thames, KT12 3LB | Walton-on-Thames | 36 | [10 empty] | 15 | 21 | [5 empty] | 36 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 36 units in draft Local Plan. Availability and capacity discussed in Regulation 19 representation from landowner who confirmed site could accommodate housing if some of the land is surplus to health care requirements (Rep ID #1112162). Site is considered developable based on information submitted by the landowner at Regulation 19. However, no pre-app or application has been submitted to the Council to date. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Developable | 6 to 10 years
WOT36 | Bridge Motor Works, New Zealand Avenue, Walton-On-Thames, KT12 1AU | Walton-on-Thames | 35 | [10 empty] | 15 | 20 | [5 empty] | 35 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 35 units in draft Local Plan. Council received confirmation from landowner that site is available for development at the capacity identified in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. Landowner confirmed site is deliverable in the 1-5 yr period of the Plan. However, no pre-app or application has been submitted to the Council. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 20 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2032/33 - 2033/34. | Developable | 6 to 10 years
WOT37 | 35 to 38 and land north of Mellor Close, Walton-on-Thames, KT12-3RX | Walton-on-Thames | 0 | [17 empty] | 0 | Identified in 2018 Urban Capacity Study [HOU012] but wasn't considered deliverable. The Council considered the site could be developed through a flatted development and allocated it for 5 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Not enough evidence
WEY1 | 75 Oatlands Drive, Weybridge, KT13 9LN | Weybridge | 0 | [17 empty] | 0 | Site allocated for 9 units in draft Local Plan. Council review of housing trajectory in support of appeal inquiry of refused application 2023/0962 for Land North of Raleigh Drive, Claygate concluded 9 units is not achievable and the site will likely come forward as a windfall development. | Allocated quantum unachievable. Will fall into windfall.
WEY2 | 9 and rear of 11 and 13 Hall Place Drive | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence
WEY3 | 24-26 Church Street, Weybridge, KT13 3DX | Weybridge | 15 | [9 empty] | 15 | [7 empty] | 15 | Identified through pre-app discussion between landowner and Council on scheme of 15 units in 2020. Officers concluded principle of development is acceptable. However, no response received to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. No further pre-app or palnning application submitted. Site considered to be developable in light of the pre-app evidence. As the site is a small major development (10 - 20 units) and could be built out relatively quickly if an application were to come forward in the next 5 years. Assuming around 1 yr for determination, then applying the average build of rate of 3 yrs to completion from decision for scheme of 10 - 49 units in the Borough would expect completion in 2032/33. | Developable | 6 to 10 years
WEY4 | Quadrant Courtyard, Weybridge, KT13 8DR | Weybridge | 0 | [17 empty] | 0 | EBC owned site allocated for 15 units in the draft Local Plan. EBC AMPS confirmed in May 2024 that scheme of up to 18 units has been worked through and found to be unviable, with the conclusions finding that reduction of the quantum results in scheme becoming more unviable. | No longer available
WEY5 | Weybridge Hospital and car park, 22 Church Street Weybridge KT13 8DW | Weybridge | 30 | [10 empty] | 15 | 15 | [5 empty] | 30 | NHS owned site identified in 2018 Urban Capacity Study [HOU012] and allocated for 30 units in draft Local Plan. NHS property services confirmed 30 units achievable in their Regulation 19 representation (ID #1112162). No application or pre-app submitted to Council. Site is considered developable in light of evidence in urban capacity study and corroboration by the NHS. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Developable | 6 to 10 years
WEY6 | Weybridge Centre for the Community, Churchfield Place, Weybridge, KT13 8BZ | Weybridge | 8 | [10 empty] | 8 | [6 empty] | 8 | EBC owned site allocated for 8 units in the draft Local Plan. In May 2024 EBC AMPS confirmed they are working on the Weybetter Weybridge scheme which will include the site and considered delivery in the 6 - 10 year period would be achievable. Delivery anticipated end of 6 - 10 yr period (2033/34) giving around 5-6 yrs for a scheme to be worked up and submitted and 4 yrs for determination and completion. | Developable | 6 to 10 years
WEY7 | Oak House, 19 Queens Road, Weybridge | Weybridge | 0 | [17 empty] | 0 | Allocated for 10 units in draft Local Plan. Site is under construction under outline PP 2021/3517 for net 10 units, with commencement (demolition) on site in March 2023. RMs condition 1 of 2021/3517 approved in May 2023. No other RMs to resolve. Discharge of all precommencement conditions confirmed. Including 5 (Material Samples) and 10 (Construction Method Statement) under 2022/3412 confirmed in Feb. 2023; 14 (Tree pre-commencement meeting) under 2023/0173 in Mar. 2023; 19 (Surface water drainage scheme) under 2023/0245 confirmed in May 2023; 21 (Secure by Design) under 2023/0483 confirmed in Jun. 2023. Construction able to start from Jun. 2023. Expect completion 2.5 yrs after commencement (winter 2025) in line with average build out rates for sites of 10 - 49 units in the Borough. | Deliverable | 1 to 5 years
WEY8 | Garages to the west of 17 Grenside Road Weybridge KT13 8PY | Weybridge | 0 | [17 empty] | 0 | PA Housing site allocated for 5 units in draft Local Plan. Application for full PP 2022/0397 for 3 units submitted in Feb. 2022 under consideration. Made valid in Apr. 2022 and comments due by Mar. 2023. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Deliverable but will fall into windfall category. | 6 to 10 years
WEY9 | Heath Lodge, St Georges Avenue | Weybridge | 0 | [17 empty] | 0 | Site allocation WEY9 allocated for 6 units in draft Local Plan. Applicant - Surrey Rest Homes Limited. Contacted agent at Union Arch 15 May 2024 who confirmed scheme is implemented and nearing completion with just internal fit out to complete. Completion anticipated by Sep. 2024. | Deliverable | 1 to 5 years
WEY10 | 8 Sopwith Drive, Brooklands Industrial Park | Weybridge | 0 | [17 empty] | 0 | Allocated for employment floorspace.
WEY11 | 9 Cricket Way, Weybridge | Weybridge | 0 | [17 empty] | 0 | Allocated for 5 units in draft Local Plan. West of site is under construction under 2022/2631 for net 4 units, with commencement on site in Feb. 2024. Discharge of conditions 9 (Tree pre-commencement meeting - with tree protection) and 13 (Tree planting and maintenance) under 2023/2383 confirmed in Nov. 2023; condition 3 (Materials samples) and 7 (Ecological enhancement plan) under 2023/2531 confirmed in Nov. 2023. Expect completion 2 yrs after commencement (Feb. 2026) in line with average build out rates for sites of 1 - 9 units in the Borough. | Deliverable | 1 to 5 years
WEY12 | Locke King House, 2 Balfour Road, Weybridge | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence
WEY13 | York Road Car Park, Weybridge | Weybridge | 0 | [17 empty] | 0 | EBC owned site allocated for 8 units in draft Local Plan. EBC AMPS confirmed that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY14 | HFMC House, New Road and 51 Prince's Road Weybridge KT13 9BN | Weybridge | 6 | [8 empty] | 6 | [8 empty] | 6 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 6 units in the draft Local Plan. Council did not receive a response confirming availability for development to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study but no pre-app or application has been submitted. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
WEY15 | Floors above Waitrose, 62 High Street, Weybridge KT13 8BL | Weybridge | 9 | [8 empty] | 9 | [8 empty] | 9 | EBC owned site allocated for 9 units in the draft Local Plan. EBC AMPS confirmed in May 2024 that they will be bringing forward a PA for change of use of the existing office to residential in the next 5 yrs. Anticipate PP recieved in 1 - 5 yr period as site is allocated for minor development (less than 10 units), an application for which can be worked up quickly, assuming around a year for the application to be determined. Then applying the average build of rate of 3 yrs to completion from decision for scheme of 1 - 9 units in the Borough would expect completion in 2031/32. | Developable | 6 to 10 years
WEY16 | Weybridge Library, Church Street, Weybridge | Weybridge | 0 | [17 empty] | 0 | SCC owned site allocated for 30 units in draft Local Plan. Council received confirmation from SCC that site is no longer available for housing development in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. SCC confirmed site is now being held for use as a community hub. EBC were consulted on PP 2023/2312 granted in Sep. 2023 for change of use to new community hub (F1, F2 and E uses). | No longer available for residential (C3) development
WEY17 | Garages to the rear of Broadwater House Grenside Road Weybridge KT13 8PZ | Weybridge | 0 | [17 empty] | 0 | PA Housing Allocated in 20 units in draft Local Plan due to typo should have read 2 units to reflect application for full PP 2022/0395 for 2 units submitted in Feb. 2022 under consideration. Made valid in Apr. 2022 and comments due by Jun. 2023. Decision target date Dec. 2023. Council allocated a number of small PA Housing sites that have PP or applications going through the development management process. Decisions on a number of the applications, including this site, have been delayed. As such, site will likely come forward as windfall development. | Developable but will fall into windfall category. | 6 to 10 years
WEY18 | 59-65 Baker St, Weybridge KT13 8AH | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY19 | Shell Petrol Filling Station 95 Brooklands Road Weybridge KT13 0RP | Weybridge | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 5 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY20 | Garages at Brockley Combe, Weybridge | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY21 | 35-47 Monument Hill, Weybridge KT13 8RN | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY22 | 2-8 Princes Road Weybridge KT13 9BQ | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY23 | Weybridge Bowling Club 19 Springfield Lane Weybridge KT13 8AW | Weybridge | 22 | [10 empty] | 22 | [6 empty] | 22 | Allocated for 22 units in draft Local Plan. Application for outline PP 2022/2598 for 30 units refused in Nov. 2022. No subsequent applications submitted. Reasons for refusal include: 1. No sufficient justification has been provided for the loss of a community facility. 2. Development, by reason of the lack of a Unilateral Undertaking, would fail to make a contribution to the provision of affordable housing. 3. Development, by virtue of its massing, width and height, is likely to result in an unduly prominent and incongruous addition to the detriment of the character of the area. 4. Proposal, by virtue of the three/four-storey scale of the building and orientation of the properties in relation to the sun's path, is likely to result in loss of light and overbearing impact on Nos. 5-15 Springfield Lane and flats within the building currently under construction and reaching completion to the north of the application site. 5. Proposed access, by reason of its proximity to neighbouring residential properties on the opposite side of Springfield Lane, would result in an unacceptable level of disturbance and significant harm to the amenity of the occupiers of the neighbouring properties. 6. Proposed development would result in a significant increase in vehicle movements over the existing development and it has not been demonstrated that the required visibility splays are achievable within land under the applicant's control. 7. There is insufficient evidence to demonstrate the developments impact upon archaeology is acceptable. Refused scheme was of greater density than the allocation proposed in the draft Plan and did not seek to retain the existing community use on the site. Council considers that a scheme of reduced density in line with the proposed allocation that sought to retain the existing use could overcome the reasons for refusal. Site is therefore considered developable. Contacted agent at Taylor Cox Associates of refused application on 23 May 2024 who could not confirm if any work on a subsequent application was being undertaken. As the site is a relatively small major development (20 - 49 units) and the lead in times can be relatively short the Council anticipates the site could come forward in the 6 - 10 yr period of the Plan. Anticipate around 1 yr for sites of 10 - 49 units to go from validation of an application to decision and average 3 yrs from decision to first completion. If PP were submitted and approved in the 1 - 5 yr period, giving 5 years for a scheme to be worked up, could anticipate completions from 2033/34. | Developable | 6 to 10 years
WEY24 | 181 Oatlands Drive, Weybridge KT13 9DJ | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence
WEY25 | The Old Warehouse, 37A Church Street, Weybridge KT13 8DG | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence
WEY26 | The Heights | Weybridge | 0 | [18 empty] | Employment floorspace allocation. Site has PP. | Site has Planning Permission
WEY27 | Oatlands car park, Oatlands Drive, Weybridge | Weybridge | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 8 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY28 | 179 Queens Road Weybridge KT13 0AH | Weybridge | 9 | [13 empty] | 9 |  |  |  | 9 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 9 units in the draft Local Plan. Council received a response confirming an interest in development in 11 to 15 years to the 2023 land ownership and availability checks carried out to inform the 2023 Land Availability Study. The site is considered developable based on the evidence in the urban capacity study and land owner checks but no pre-app or application has been submitted. | Developable | 11 to 15 years
WEY29 | 1 Princes Road Weybridge KT13 9TU | Weybridge | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 19 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY30 | NHS North West, 58 Church Street, Weybridge KT13 8DP | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY31 | Weybridge Delivery Office, Elmgrove Road | Weybridge | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 5 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY32 | Baker Street car park, Weybridge | Weybridge | 7 | [14 empty] | 7 |  |  | 7 | EBC owned site allocated for 7 units in draft Local Plan. No plans have been developed yet but EBC AMPS confirmed in May 2024 that the site is considered developable and can be brought forward for delivery in the 11 - 16 yr period of the Plan. Delivery anticipated in the 11 - 16 yr period from 2037/38), giving around 10 yrs for a scheme to be worked up and submitted and 4 yrs for determination and completion. | Developable | 11 to 15 years
WEY33 | GlaxoSmithKline, St. Georges Avenue | Weybridge | 120 | [7 empty] | 60 | 60 | [8 empty] | 120 | Identified in 2018 Urban Capacity Study [HOU012] and allocated for 100 units in draft Local Plan. Site capacity and design work undertaken by landowner and submitted with their Regulation 19 representation confirms site is developable and capacity is able to achievable 120 units. An application has not been submitted but the site is considered to be developable based on the evidence submitted by the landowner at Regulation 19. Landowners are planning to move the use on the site to the Heights emplyoment site. PP 2023/3281 granted in May 2024 for employment and research floorspace to enable this move. Contacted agent Vail Williams 23 May 2024 who confirmed with PP 2023/3281 secured they will look to undertake a staggered move to the new facility at the Heights with the site expected to be vacant by late 2027/early 2028. Allowing time for securing PP and contractors they anticipate a start of construction on site in mid 2029 with construction estimated to be 12 - 18 months and completion in late 2030. | Developable | 6 to 10 years
WEY34 | Woodlawn, Hanger Hill and 2 Churchfields Avenue, Weybridge, KT13 9XU | Weybridge | 0 | [17 empty] | 0 | Allocated in draft Local Plan for 11 units. Council received confirmation from landowner that site is no longer available in response to land ownership and availability checks carried out to inform the 2023 Land Availability Assessment. | No longer available
WEY36 | 1-8 Dovecote Close, Weybridge, KT13 8PW | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
WEY37 | Foxholes, Weybridge KT13 0BN | Weybridge | 0 | [17 empty] | 0 |  | Not enough evidence.
Total |  |  | 1853 |  | 0 | 0 | 37 | 18 | 50 | 142 | 178 | 188 | 185 | 203 | 120 | 49 | 105 | 164 | 179 | 186 | 1804

## Windfall allowance
Data source: No. of PPs that resulted in net gain of 1 - 4 units - https://www.elmbridge.gov.uk/planning/planning-policy-and-guidance/monitoring-reports
Monitoring year | Windfall rate
2012/13 | 85
2013/14 | 84
2014/15 | 96
2015/16 | 78
2016/17 | 88
2017/18 | 73
2018/19 | 149
2019/20 | 47
2020/21 | 84
2021/22 | 97
2022/23 | 66
2023/24 | 49
Total | 827
Average | 82.7
*Windfall sites defined as sites of 1 - 4 net units

## Plan period trajectory
|  |  | Years 1 -5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
| 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total
Completions | 236 | 406
Under construction (incl. site allocations under construction) |  |  | 423 | 225 | 102 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 763
Resolution to Grant |  |  | 0 | 27 | 160 | 97 | 120 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426
PP for medium/large sites - 10+ units (incl. site allocations with PP) |  |  | 52 | 30 | 46 | 215 | 70 | 69 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511
PP for small sites <10 units (incl. site allocations with PP) |  |  | 62 | 59 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196
Small site non-implementation discount (- 10%) |  |  | 55.8 | 53.1 | 67.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.4
Site allocations (not incl. site allocations under construction or with PP) |  |  | 0 | 0 | 37 | 18 | 50 | 142 | 178 | 188 | 185 | 203 | 120 | 49 | 105 | 164 | 179 | 186 | 1804
Windfall (from yr 4) | [5 empty] | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 82.7 | 1075.1
Total Supply | 236 | 406 | 530.8 | 335.1 | 412.5 | 412.7 | 335.7 | 315.7 | 289.7 | 270.7 | 267.7 | 285.7 | 202.7 | 131.7 | 187.7 | 246.7 | 261.7 | 268.7 | 4755.5

## Plan period HLS
Local Plan Housing Requirement Trajectory |  |  | Years 1 - 5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
| 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total
Housing Requirement | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 452 | 8136
Supply | 236 | 406 | 530.8 | 335.1 | 412.5 | 412.7 | 335.7 | 315.7 | 289.7 | 270.7 | 267.7 | 285.7 | 202.7 | 131.7 | 187.7 | 246.7 | 261.7 | 268.7 | 5397.5
Annual Shortfall (-) / Oversupply (+) | -216 | -46 | 78.8 | -116.9 | -39.5 | -39.3 | -116.3 | -136.3 | -162.3 | -181.3 | -184.3 | -166.3 | -249.3 | -320.3 | -264.3 | -205.3 | -190.3 | -183.3 | -2738.5
Cumulative Shortfall (-) / Oversupply (+) | -216 | -262 | -183.2 | -300.1 | -339.6 | -378.9 | -495.2 | -631.5 | -793.8 | -975.1 | -1159.4 | -1325.7 | -1575 | -1895.3 | -2159.6 | -2364.9 | -2555.2 | -2738.5 | -2738.5
Standard Method Housing Trajectory |  |  | Years 1 - 5 |  |  |  |  | Years 6 - 10 |  |  |  |  | Years 11 - 16
| 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | Total
Housing Requirement | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 11700
Supply | 236 | 406 | 530.8 | 335.1 | 412.5 | 412.7 | 335.7 | 315.7 | 289.7 | 270.7 | 267.7 | 285.7 | 202.7 | 131.7 | 187.7 | 246.7 | 261.7 | 268.7 | 5397.5
Annual Shortfall (-) / Oversupply (+) | -414 | -244 | -119.2 | -314.9 | -237.5 | -237.3 | -314.3 | -334.3 | -360.3 | -379.3 | -382.3 | -364.3 | -447.3 | -518.3 | -462.3 | -403.3 | -388.3 | -381.3 | -6302.5
Cumulative Shortfall (-) / Oversupply (+) | -414 | -658 | -777.2 | -1092.1 | -1329.6 | -1566.9 | -1881.2 | -2215.5 | -2575.8 | -2955.1 | -3337.4 | -3701.7 | -4149 | -4667.3 | -5129.6 | -5532.9 | -5921.2 | -6302.5 | -6302.5

## 5 yr HLS
| 5 year Housing Land Supply Calculation | Local Plan Housing Requirement | Standard Method Housing Requirement
A | Annual Housing Requirement | 452 | 650
B | Total Requirement over 5 yrs | 2260 | 3250
C | Shortfall | 262 | 658
D = B+C | Total + Shortfall | 2522 | 3908
E = 5% of D | 5% Buffer | 126.1 | 195.4
F = D+E | Total Housing Requirement | 2648.1 | 4103.4
G = F/5 | Annualised Housing Requirement | 529.62 | 820.68
H | Under construction | 763 | 763
I | Planning Permission (Medium & Large Sites) | 413 | 413
J | Planning Permission (Small Sites) | 196 | 196
K | Small Site Non-implementation discount (10%) | 19.6 | 19.6
L = J-K | Planning Permissions - 10% discount | 176.4 | 176.4
M | Resolution to Grant | 404 | 404
N | Site allocations | 105 | 105
O | Windfall (from yr 4) | 165.4 | 165.4
P = H+I+L+M+N+O | Total Supply | 2026.8 | 2026.8
Q = G/P | 5 yr HLS | 3.8269 | 2.4697
Shortfall/Oversupply |  | 621.3 | 2076.6

## Distribution of development
UC |  |  | PP (small) |  | PP (medium & large) |  | Resolution |  | Site allocations |  |  | PP (small site) | 10% | -10%
Row Labels | Sum of Total |  | Row Labels | Sum of Total | Row Labels | Sum of Total | Row Labels | Sum of Total | Row Labels | Sum of Total | Claygate | 4 | 0.4 | 3.6
Claygate | 67 |  | Claygate | 4 | Cobham & Oxshott | 10 | Weybridge | 426 | Claygate | 22 | Cobham & Oxshott | 42 | 4.2 | 37.8
Cobham & Oxshott | 141 |  | Cobham & Oxshott | 42 | Esher | 39 | Grand Total | 426 | Cobham, Oxshott and Stoke D'Abernon | 142 | Dittons | 7 | 0.7 | 6.3
Dittons | 89 |  | Dittons | 7 | Molesey | 60 |  |  | Esher | 776 | Esher | 18 | 1.8 | 16.2
Esher | 112 |  | Esher | 18 | Thames Ditton | 12 |  |  | Hersham | 170 | Hersham | 11 | 1.1 | 9.9
Hersham | 34 |  | Hersham | 11 | Walton-on-Thames | 108 |  |  | Molesey | 121 | Molesey | 27 | 2.7 | 24.3
Molesey | 71 |  | Molesey | 27 | Weybridge | 282 |  |  | Thames Ditton, Long Ditton, Hinchley Wood and Weston Green | 104 | Thames Ditton | 2 | 0.2 | 1.8
Thames Ditton | 32 |  | Thames Ditton | 2 | Grand Total | 511 |  |  | Walton-on-Thames | 243 | Walton-on-Thames | 42 | 4.2 | 37.8
Walton-on-Thames | 57 |  | Walton-on-Thames | 42 |  |  |  |  | Weybridge | 226 | Weybridge | 43 | 4.3 | 38.7
Weybridge | 160 |  | Weybridge | 43 |  |  |  |  | (blank) |  | Total | 196 | 19.6 | 176.4
Grand Total | 763 |  | Grand Total | 196 |  |  |  |  | Grand Total | 1804
Settlement Area | No. of units | % of total
Claygate | 92.6 | 2.516%
Cobham & Oxshott, Stoke D'Abernon and Downside | 330.8 | 8.988%
East & West Molesey | 276.3 | 7.507%
Esher | 943.2 | 25.63%
Hersham | 213.9 | 5.812%
Long Ditton, Thames Ditton, Hinchley Wood & Weston Green | 245.1 | 6.66%
Walton-on-Thames | 445.8 | 12.11%
Weybridge | 1132.7 | 30.78%
Total | 3680.4 | 100%